## V1 matrix
ID | Reference | Requirement | Milestone | Status | Owner | Dependencies | Acceptance criteria | Deferred scope | Evidence | Notes
V1-MOD-01 | V1 Modules | Chart of Accounts | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account table + AccountService + /accounts API + default UK chart (UK_SMALL_COMPANY v1). migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: tests/api/ledger.test.ts (chart), tests/db/ledger.test.ts (account guards), packages/contracts/src/ledger.test.ts
V1-MOD-02 | V1 Modules | Customers | M4 | MISSING | Engineering | V1-CON-01..05 | A contact can hold the CUSTOMER role with payment terms, default currency, default tax treatment and credit limit; filter/search by role; company-scoped; both roles allowed; archived customers rejected on new documents. | Statements, dunning |  | V0 contacts exist (master data); customer role/terms are V1
V1-MOD-03 | V1 Modules | Suppliers | M4 | MISSING | Engineering | V1-CON-01..05 | SUPPLIER role with payment terms, default expense account, bank details (field-encrypted, never in lists or logs); both roles allowed; archived suppliers rejected on new documents. | Supplier portal
V1-MOD-04 | V1 Modules | Sales | M5 | IMPLEMENTED | Engineering | M2, M3, M4, V1-MOD-02 | Invoice lifecycle DRAFT -> APPROVED (posted) -> paid; numbering without gaps per company; lines with VAT and currency; posting Dr receivables / Cr revenue / Cr output VAT through the PostingService with source link both ways; documents attach; AI can propose but never approve; positive, negative, reversal, VAT and period-lock tests. | Recurring invoices, quotes, online payment | Invoices: DRAFT (no number, no ledger effect; revisioned lines) -> APPROVED (numbered without gaps from a locked sequence the database checks; customer snapshot; amounts recomputed with verified VAT rates; posted as SALES_INVOICE Dr receivables / Cr revenue / Cr output VAT; journal and document linked both ways; immutable) or DISCARDED; attachments through the evidence graph; drafts from ACCEPTED AI proposals, approval by people only; positive, negative, VAT (standard, zero, exempt; exclusive, inclusive), period-lock and correction-by-credit-note tests. 'Paid' is reached by receipts and credit notes (M5b), with statements and aged receivables. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts Tests: tests/platform/sales-receipts.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts | M5a and M5b delivered (DEC-026, DEC-032).
V1-MOD-05 | V1 Modules | Purchases | M6 | MISSING | Engineering | M3, M4, V1-MOD-03 | Bills with VAT and currency; posting Dr expense/asset / Dr input VAT / Cr payables; duplicate-bill check; same test set as sales. | Purchase orders, expense claims
V1-MOD-06 | V1 Modules | Credit Notes | M5 | IMPLEMENTED | Engineering | V1-MOD-04 | A sales credit note references its invoice (full linkage), reverses or adjusts the economic effect including VAT, cannot exceed the invoice balance, and is traceable from both documents. | Refund automation | A sales credit note references one approved invoice of the same customer and currency (database rule), uses only the invoice's VAT codes at the invoice's rate versions (DEC-029), cannot exceed the invoice outstanding (service and database), is allocated to its invoice in the same transaction and is traceable from both documents. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts
V1-MOD-07 | V1 Modules | Debit Notes | M6 | MISSING | Engineering | V1-MOD-05 | Purchase credit note / debit note with the same linkage rules against the bill. | Supplier refund workflow
V1-MOD-08 | V1 Modules | Receipts | M5 | IMPLEMENTED | Engineering | V1-MOD-04 | Receipt Dr bank / Cr receivables; allocation to one or more invoices; part payments; overpayments to an unallocated balance; realised FX difference when currencies differ. | Direct debit integration | Receipts post SALES_RECEIPT Dr bank or cash / Cr trade receivables when recorded; allocation to one or more invoices at entry or later; part payments; overpayments kept as unallocated credit (reducing open balance, credit-limit use and ageing); realised FX on every allocation when rates differ (gain 30.00 then loss 20.00, hand-calculated); duplicate check with reason; reversal of unallocated receipts at their own rate; database guards on immutability, allocation and reversal. Tests: tests/platform/sales-receipts.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts
V1-MOD-09 | V1 Modules | Payments | M6 | MISSING | Engineering | V1-MOD-05 | Payment Dr payables / Cr bank; allocation, part payments; realised FX difference. | Payment runs and bank file export
V1-MOD-10 | V1 Modules | Bank Accounts | M7 | MISSING | Engineering | M1 | Bank accounts as ledger accounts with bank details (field-encrypted), account currency, opening balance via M2 controls. | Open Banking feeds (V11)
V1-MOD-11 | V1 Modules | Cash | M6 | MISSING | Engineering | M1 | Cash accounts and cash transactions with negative-cash alerts. | Petty-cash float management
V1-MOD-12 | V1 Modules | VAT foundation | M4 | MISSING | Engineering + qualified tax reviewer | V1-VAT-01..15 | Section 5 of v1-plan.md: all V1-VAT acceptance criteria met with verified sources. | Cash accounting, Flat Rate Scheme, partial exemption, capital goods, margin schemes, OSS |  | Foundation only; MTD returns are V5
V1-MOD-13 | V1 Modules | Journals | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | POST /journals (manual and opening-balance sources), GET /journals[/id], POST /journals/{id}/reverse; all through the PostingService. Tests: tests/platform/posting-service.test.ts, tests/api/ledger.test.ts | Posting only: no draft or approval step for manual journals (open decision 5 in v1-plan.md)
V1-MOD-14 | V1 Modules | General Ledger | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | GET /ledger (general ledger per account, running balance, keyset paging recomputed per page). Tests: tests/platform/posting-service.test.ts (one page equals paged), tests/api/ledger.test.ts
V1-MOD-15 | V1 Modules | Trial Balance | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | GET /reports/trial-balance (as at a date or a period with movement; journal lines only; balanced flag; suspense warning; drill-down parameters). Tests: tests/platform/posting-service.test.ts, tests/api/ledger.test.ts (independent SQL check)
V1-MOD-16 | V1 Modules | P&L | M8 | MISSING | Engineering | M8, trial balance | P&L is computed from the trial balance via the reporting mapping, never from source transactions; every figure drills to account -> journal -> source -> document; comparatives by period. | FRS 102/105 layouts (V2)
V1-MOD-17 | V1 Modules | Balance Sheet | M8 | MISSING | Engineering | M8, trial balance | Balance sheet from the trial balance including current-year profit; balances; drill-down as P&L. | FRS 102/105 layouts (V2)
V1-MOD-18 | V1 Modules | Reconciliation | M7 | MISSING | Engineering | M7 | Bank reconciliation states matched / partial / unmatched / suggested / manual override with audit; reconciled balance proves to the statement. | AI suggestions (V6)
V1-MOD-19 | V1 Modules | Accounting Periods (explicit states and close controls) | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | OPEN<->CLOSED->LOCKED->CLOSED with database-enforced graph, period:manage / period:lock, mandatory reasons, audit before/after, events, concurrency-safe. Tests: tests/platform/posting-service.test.ts (period controls), tests/db/ledger.test.ts, tests/api/ledger.test.ts | Close controls beyond 'ledger balances' are added by M2-M5 as their data exists (see MAN-ACC-08)
V1-ARC-01 | V1 Accounting Architecture | Source document -> transaction service -> PostingService -> journal -> journal lines -> ledger | M1 | PARTIALLY IMPLEMENTED | Engineering | Source modules M5-M7 | Every source document posts through the PostingService; no module writes the ledger; each source transaction links to its journal and back. | - | PostingService -> journal -> journal_line -> ledger exists with MANUAL, OPENING_BALANCE and REVERSAL sources. No source-document transaction services yet (M2+). Tests: tests/platform/posting-service.test.ts M5a: Sales documents post only through the PostingService (SALES_INVOICE, SALES_CREDIT_NOTE, SALES_ALLOCATION_FX) and link to their journals both ways; architecture test: one writer of the sales tables, which never writes journals. | M1 delivers PostingService + journals + ledger with manual and reversal sources; each later milestone adds a transaction service
V1-ARC-02 | V1 Accounting Architecture | Financial statements are never calculated from source transactions (Trial Balance -> P&L / Balance Sheet) | M1 | PARTIALLY IMPLEMENTED | Engineering | M8 | P&L and balance sheet read the trial balance only; a test fails if a report queries a source table. | - | Trial balance and general ledger aggregate journal_line only (architecture: no report reads source tables). P&L and balance sheet are M5. Tests: tests/platform/posting-service.test.ts, tests/api/ledger.test.ts | Trial balance in M1; statements in M5, both from journal lines only
V1-COA-01 | V1 Chart of Accounts | Account code | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.code (unique per company, 1-20 chars). migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-02 | V1 Chart of Accounts | Account name | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.name. migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-03 | V1 Chart of Accounts | Account type | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.type (ASSET/LIABILITY/EQUITY/INCOME/EXPENSE). migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-04 | V1 Chart of Accounts | Account subtype | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.subtype (registry constrained to the type). migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-05 | V1 Chart of Accounts | Control account flag | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.is_control + control_kind (receivables, payables, VAT, bank, cash, suspense, retained earnings); manual journals cannot post to control accounts. migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-06 | V1 Chart of Accounts | Tax treatment | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.tax_treatment (account level). migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts | Account-level treatment in M1; VAT codes on lines arrive with the VAT foundation (M2)
V1-COA-07 | V1 Chart of Accounts | Reporting mapping | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.reporting_mapping from a versioned report-line registry, checked against the type. migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-COA-08 | V1 Chart of Accounts | Active dates | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | account.active_from / active_to enforced on every posting date; deactivation cannot precede the last posting. migration 20260106000000_v1_ledger_core; packages/accounting; apps/api/src/ledger; ADR-44..48. Tests: packages/contracts/src/ledger.test.ts, tests/api/ledger.test.ts, tests/db/ledger.test.ts
V1-POST-01 | V1 Posting Engine | PostingService is the sole service authorised to post ledger entries | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Single writer enforced three ways: architecture test (only packages/accounting/src/posting.ts writes journal/journal_line/ledger_sequence; only it sets app.posting; platform/AI/worker cannot import the package), database guard (insert refused without the transaction flag), privileges. Tests: tests/unit/architecture.test.ts, tests/db/ledger.test.ts | Honest limit: the flag is application-asserted (same trust boundary as tenant context)
V1-POST-02 | V1 Posting Engine | Validate: balanced journal | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Application check + deferred constraint trigger at commit (header agrees with lines, contiguous numbering, reversal mirrors original). Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts
V1-POST-03 | V1 Posting Engine | Validate: valid accounts | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Accounts must exist in the company (composite FK), be active on the journal date, and not be control accounts for manual sources. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts, tests/api/ledger.test.ts
V1-POST-04 | V1 Posting Engine | Validate: valid period | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Period must exist, contain the date and be OPEN; period row locked FOR SHARE so a concurrent close cannot race. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts (race test), tests/api/ledger.test.ts
V1-POST-05 | V1 Posting Engine | Validate: VAT treatment | M4 | IMPLEMENTED | Engineering + qualified tax reviewer | M4, V1-VAT-* | A VAT validator in the posting chain refuses a posting whose VAT treatment, rate (effective on the tax point) or amounts are inconsistent. | - | VAT validation in the posting chain (see V1-VAT-14). Tests: tests/platform/vat.test.ts, tests/db/vat.test.ts | Validator chain exists from M1; the VAT validator ships with the VAT foundation
V1-POST-06 | V1 Posting Engine | Validate: currency | M3 | PARTIALLY IMPLEMENTED | Engineering | M3 | Single-currency limitation is explicit now (V1-FX-10); full multi-currency validation (transaction currency, rate, original values) delivered by M3. | - | Currency validated: journals are in the company base currency and amounts respect its minor units (application + database). Foreign-currency documents, FX rates and revaluation are NOT supported (open decision 1). Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts | Base currency of the company only; foreign-currency postings and FX revaluation are not in V1 scope until a decision is recorded
V1-POST-07 | V1 Posting Engine | Validate: source reference | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Registered source type required; REVERSAL must name the reversed journal; other sources require a source id; idempotency key per company with content hash. Tests: tests/platform/posting-service.test.ts, packages/contracts/src/ledger.test.ts
V1-POST-08 | V1 Posting Engine | Validate: permissions | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Source-specific permission evaluated for the journal's company through the central authoriser; AI actors refused; system actors limited to system sources. Tests: tests/platform/posting-service.test.ts, tests/api/ledger.test.ts (roles x posting), tests/api/permissions.test.ts
V1-EX-01 | V1 Sales Example | Sale: Dr Trade Receivables / Cr Revenue / Cr Output VAT | M5 | IMPLEMENTED | Engineering | V1-MOD-04 | Sales example posts exactly Dr receivables / Cr revenue / Cr output VAT for standard, zero-rated and exempt lines, with tests. | - | An approved invoice posts exactly Dr trade receivables (gross) / Cr revenue (net per line) / Cr output VAT (per VAT-coded line), with standard, zero-rated and exempt lines and VAT-inclusive entry, hand-calculated. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts
V1-EX-02 | V1 Purchase Example | Purchase: Dr Expense/Asset / Dr Input VAT / Cr Trade Payables | M6 | MISSING | Engineering | V1-MOD-05 | Purchase example posts Dr expense or asset / Dr input VAT / Cr payables. | -
V1-EX-03 | V1 Receipt | Receipt: Dr Bank / Cr Trade Receivables | M5 | IMPLEMENTED | Engineering | V1-MOD-08 | Receipt example Dr bank / Cr receivables. | - | A receipt posts exactly Dr bank (or cash) / Cr trade receivables, in functional and foreign currency; its journal links to the receipt both ways. Tests: tests/platform/sales-receipts.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts
V1-EX-04 | V1 Payment | Payment: Dr Trade Payables / Cr Bank | M6 | MISSING | Engineering | V1-MOD-09 | Payment example Dr payables / Cr bank. | -
V1-EX-05 | V1 Credit Notes | Credit notes reverse or adjust the original economic effect with full source linkage | M5 | PARTIALLY IMPLEMENTED | Engineering | V1-MOD-06, V1-MOD-07 | Credit notes reverse or adjust the original with full source linkage in both directions. | - | Sales: a credit note mirrors the credited lines and VAT, linked both ways (credit note -> invoice; invoice lists its credit notes) and allocated. Purchases (debit notes) are M6. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts | Sales credit notes M2; purchase (debit) notes M3. The reversal primitive and source linkage ship in M1
V1-BANK-01 | V1 Bank | Bank accounts | M7 | MISSING | Engineering | M7 | Bank accounts created and linked to ledger accounts. | -
V1-BANK-02 | V1 Bank | Statement imports | M7 | MISSING | Engineering | M7 | CSV statement import as an asynchronous job with progress, retry and duplicate detection (job_record); other formats are decisions. | OFX/MT940/Open Banking |  | Asynchronous job with progress; file formats to be decided in the M4 design
V1-BANK-03 | V1 Bank | Transactions | M7 | MISSING | Engineering | M7 | Imported transactions stored immutably with their import batch; never edited. | -
V1-BANK-04 | V1 Bank | Reconciliation | M7 | MISSING | Engineering | M7 | Reconciliation workflow on transactions. | -
V1-BANK-05 | V1 Bank | Unmatched items | M7 | MISSING | Engineering | M7 | Unmatched list with ageing and a count visible on the dashboard. | -
V1-BANK-06 | V1 Bank | Transfers | M7 | MISSING | Engineering | M7 | Transfers between bank accounts post one balanced journal; both statements match it. | -
V1-BANK-07 | V1 Bank | Bank charges | M7 | MISSING | Engineering | M7 | Bank charges recognised from statements and posted to the charges account. | -
V1-BANK-08 | V1 Bank | Interest | M7 | MISSING | Engineering | M7 | Interest recognised from statements and posted to interest income/expense. | -
V1-REC-01 | V1 Reconciliation | Matched | M7 | MISSING | Engineering | M7 | Matched pairs link a statement line to ledger entries and cannot be changed without an audited un-match. | -
V1-REC-02 | V1 Reconciliation | Partially matched | M7 | MISSING | Engineering | M7 | A statement line can be matched in parts; the unmatched remainder stays visible. | -
V1-REC-03 | V1 Reconciliation | Unmatched | M7 | MISSING | Engineering | M7 | Unmatched items listed with age. | -
V1-REC-04 | V1 Reconciliation | Suggested matches | M7 | MISSING | Engineering | M7 | Deterministic rule-based suggestions (amount, date window, reference); a suggestion never posts. | AI suggestions (V6) |  | Rule-based suggestions; AI suggestions are V6 and may only propose
V1-REC-05 | V1 Reconciliation | Manual override with audit | M7 | MISSING | Engineering | M7 | Manual matches and overrides need a reason and are audited. | -
V1-RPT-01 | V1 Reporting | Trial Balance -> P&L / Balance Sheet | M8 | MISSING | Engineering | M8 | Trial balance -> P&L / balance sheet reconcile to the cent for any period. | - |  | Trial balance in M1
V1-RPT-02 | V1 Reporting | Drill-down: Report -> account -> journal -> source transaction -> document | M8 | PARTIALLY IMPLEMENTED | Engineering | M5-M8 | Click-through from any report number to account -> journal -> source transaction -> document works for every source type; a test asserts it per source. | - | Report -> account -> journal -> source reference works (trial balance rows carry drill-down parameters; ledger lines carry journal and source). Source transaction and document links arrive with each source module. Tests: tests/api/ledger.test.ts M5a: Journal -> sales document drill path exists (source_id) and document -> journal (journal_id); report drill-down UI is M8/M9. | Report -> account -> journal in M1; source transaction and document links arrive with each source module
V1-CTL-01 | V1 Controls | Locked periods | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Closed and locked periods refuse postings (service + database); lock needs period:lock. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts, tests/api/ledger.test.ts
V1-CTL-02 | V1 Controls | Duplicate document checks | M5 | PARTIALLY IMPLEMENTED | Engineering | M5 | Duplicate documents (same contact, number, date, amount) are flagged before posting; override needs a reason. | - | Sales invoices: before approval, another approved invoice of the same customer with the same date, currency and total, or the same customer reference, refuses approval unless a reason is given (stored on the document and audited). Supplier bills (supplier's own number) are M6. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts
V1-CTL-03 | V1 Controls | Suspense account visibility | M1 | PARTIALLY IMPLEMENTED | Engineering | M8 | Suspense balance shown on the dashboard and blocks period lock unless acknowledged with a reason. | - | Trial balance warns about a non-zero suspense balance (account with control kind SUSPENSE). Dashboard alert is M5. Tests: tests/platform/posting-service.test.ts | Trial balance warning in M1; dashboard alert in M5
V1-CTL-04 | V1 Controls | Negative cash alerts | M8 | MISSING | Engineering | M7 | Negative cash/bank balances alert at posting and on the dashboard. | -
V1-CTL-05 | V1 Controls | Unposted transaction alerts | M8 | PARTIALLY IMPLEMENTED | Engineering | M5 | Draft/unposted documents older than a threshold are listed and block period close unless acknowledged. | - | Closing a period is refused while draft sales documents are dated in it unless acknowledged (acknowledgeDraftDocuments, recorded on the audit event); drafts are listed by status. An age threshold and alerting (dashboard) are M8. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts
V1-CTL-06 | V1 Controls | Audit trail | M1 | PARTIALLY IMPLEMENTED | Engineering | M5-M7 | Every source module audits its actions (created, approved, posted, voided) with before/after and reason. | - | journal.posted/reversed, account.created/updated/chart_initialised and period.closed/reopened/locked/unlocked are audited in the business transaction (before/after, reason, actor, source workflow where relevant). M2 adds ledger.request_created/approved/rejected/cancelled and ledger.policy_changed (before/after, reason). Source modules add their own events in M5+. Tests: tests/platform/posting-service.test.ts, tests/api/ledger.test.ts M5a: Sales documents audit created, updated, discarded, approved (with override reasons) and allocation events.
V1-TEST-01 | V1 Tests | Every posting rule: positive, negative, reversal, VAT and period-lock tests | M1 | PARTIALLY IMPLEMENTED | Engineering | M4 | Every posting rule has positive, negative, reversal, VAT and period-lock tests; a coverage test lists the rules and fails when one lacks a category. | - | Positive, negative, reversal and period-lock tests exist for every M1 posting rule; the VAT test arrives with the VAT validator (M2). Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts | Applied per rule as each milestone adds rules; the matrix lists the rule set tested
MAN-ACC-01 | Manifest accounting controls | Only the central PostingService can create posted ledger entries | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Single writer enforced three ways: architecture test (only packages/accounting/src/posting.ts writes journal/journal_line/ledger_sequence; only it sets app.posting; platform/AI/worker cannot import the package), database guard (insert refused without the transaction flag), privileges. Tests: tests/unit/architecture.test.ts, tests/db/ledger.test.ts | Same as V1-POST-01
MAN-ACC-02 | Manifest accounting controls | Posted journals are immutable | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | No UPDATE/DELETE/TRUNCATE privilege for the runtime role and append-only triggers (the table owner is refused too). Tests: tests/db/ledger.test.ts, tests/db/privileges.test.ts | Privileges, triggers, tests
MAN-ACC-03 | Manifest accounting controls | Corrections use reversal/adjustment journals | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Reversal journals: linked both ways, mirror enforced per account at commit, at most once, a reversal cannot be reversed, dated on/after the original, in an open period. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts, tests/api/ledger.test.ts
MAN-ACC-04 | Manifest accounting controls | Debits must equal credits | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | Application validation and a deferred database check at commit. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts | Application and deferred database check
MAN-ACC-05 | Manifest accounting controls | Every posted journal has source, user/system actor, timestamp and audit metadata | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | journal: source_type/source_id/source_reference, actor_type + posted_by_user_id, posted_at, correlation id, idempotency key; audit event and transaction.posted outbox event in the same transaction. Tests: tests/platform/posting-service.test.ts
MAN-ACC-06 | Manifest accounting controls | Every source transaction is traceable to its journal | M5 | PARTIALLY IMPLEMENTED | Engineering | M5-M7 | Every source transaction type links to its journal and back; a test enumerates source types. | - | Journal -> source via source_type/source_id/source_reference (done); source transaction -> journal is delivered per source module (M2+). M5a: Sales invoices, credit notes and allocations link to their journals and back (journal source_id; document journal_id; allocation fx_journal_id), proven by database rules. | Journal -> source in M1 (source_type/source_id); source -> journal per module
MAN-ACC-07 | Manifest accounting controls | Every report number is drillable to ledger/source evidence | M8 | MISSING | Engineering | M8 | Every report number drills to ledger and source evidence. | - |  | Same as V1-RPT-02
MAN-ACC-08 | Manifest accounting controls | Accounting periods have explicit states and close controls | M1 | PARTIALLY IMPLEMENTED | Engineering | M5-M7 | Close checks include unposted documents and unreconciled bank items. | - | Explicit period states and the transition graph are delivered and enforced; the close controls so far are 'posting stops' and 'ledger balances'. Unposted documents and unreconciled bank items are added by M2-M4. Tests: tests/platform/posting-service.test.ts, tests/db/ledger.test.ts M5a: Close control for draft sales documents dated in the period (acknowledgement recorded); unreconciled bank items follow in M7. | Same as V1-MOD-19
MAN-ACC-09 | Manifest accounting controls | Tax and reporting rules are effective-dated/versioned | M4 | PARTIALLY IMPLEMENTED | Engineering + qualified tax reviewer | M4 | VAT rates and report mappings are effective-dated in the database with source and verification status; a test proves a rate change does not alter posted history. | - | Report mappings are a versioned registry (REPORT_MAPPING_VERSION = 1, returned with every account) but not yet effective-dated in the database; VAT rates are M2. | Reporting mappings versioned in M1; VAT rates effective-dated in M2
MAN-ACC-10 | Manifest accounting controls | AI cannot silently post accounting entries or submit filings | M1 | IMPLEMENTED | Engineering | M1 (accepted) | Met - see evidence | - | PostingService refuses AI actors (ai_cannot_post); no journal source lists AI; architecture test forbids platform, the AI module and the worker from importing the accounting package. Tests: tests/platform/posting-service.test.ts, packages/contracts/src/ledger.test.ts, tests/unit/architecture.test.ts | PostingService refuses AI actors; architecture test keeps the AI module away from the posting code
XP-01 | Cross-platform 1 | Universal drill-down | M8 | MISSING | Engineering | M8 | Universal drill-down pattern available to every report. | -
XP-07 | Cross-platform 7 | Events: TransactionPosted, BankImported, InvoiceCreated | M1 | PARTIALLY IMPLEMENTED | Engineering | M5, M7 | InvoiceCreated (M5), BankImported (M7) published through the outbox. | - | transaction.posted and accounting_period.state_changed events are published through the outbox; BankImported and InvoiceCreated arrive with M4 and M2. M5a: InvoiceCreated (`invoice.created`) and `credit_note.created` are published through the outbox on approval (tests/platform/sales.test.ts); BankImported is M7. M5b adds `sales_receipt.recorded`. | TransactionPosted in M1; BankImported M4; InvoiceCreated M2
V1-DOD-01 | Manifest definition of done | UI workflows are usable (V1 screens) | M9 | MISSING | Engineering (front end) | M9 | Usable end-to-end bookkeeping screens behind flags, tested against the real API, authorisation and tenant boundaries, with accessibility checks. | Mobile portal |  | DEC-002: parallel behind feature flags
V1-CTL-07 | DEC-012 | Distinct permission `ledger:opening-balance` required for opening-balance journals | M2 | IMPLEMENTED | Engineering | M1 | Only holders of the permission can post OPENING_BALANCE; owner/admin/partner hold it, others do not; 403 and audited denial otherwise; role/permission sync tests pass. | - | Permission `ledger:opening-balance` (COMPANY scope) is required to request an opening balance; owner/admin/partner hold it, manager/accountant/bookkeeper/reviewer/client viewer do not (migration 20260107000000 + role sync). `journal:post` alone no longer suffices; `POST /journals` refuses OPENING_BALANCE. Tests: tests/api/ledger-controls.test.ts (permission matrix over 8 roles for all four new permissions, 22 cases), tests/api/permissions.test.ts (4 new probes x 8 roles), packages/contracts/src/ledger.test.ts
V1-CTL-08 | DEC-012 | Control accounts protected from ordinary manual postings; narrowly authorised adjustments need reason, evidence and audit trail | M2 | IMPLEMENTED | Engineering | M1, documents/evidence links | A CONTROL_ADJUSTMENT request needs permission `ledger:control-adjustment`, a reason of at least 20 characters and at least one evidence document readable by the requester; posting without them fails; the journal links to the request, the evidence and the approver; ordinary MANUAL journals still cannot touch control accounts. | - | CONTROL_ADJUSTMENT request needs `ledger:control-adjustment` (accountant, owner/admin/partner), a reason of at least 20 characters (service + database check), at least one evidence document that exists, belongs to the company and is readable by the requester (restricted documents indistinguishable from missing), and must touch a control account. The journal records request, requester and approver and the evidence is linked journal -> document in the evidence graph; MANUAL journals still refused on control accounts. Tests: tests/api/ledger-controls.test.ts (validation, control-account adjustment, evidence graph), tests/platform/posting-service.test.ts
V1-CTL-09 | DEC-012 | Configurable second-person approval for material opening balances and exceptional control-account adjustments | M2 | IMPLEMENTED | Engineering (build); product owner (thresholds) | V1-CTL-07, V1-CTL-08 | Per-company policy sets the materiality threshold and which request kinds need approval; above it the journal is not posted until a different person holding `ledger:approve` approves; the requester can never approve their own request; below the threshold policy may allow direct posting only if configured; approval posts through the PostingService; rejection and expiry leave the ledger untouched. | Per-account rules; delegation; multi-step chains | Per-company `ledger_policy` (ALWAYS default / ABOVE_THRESHOLD with strictly-greater materiality threshold, expiry 1-90 days; no NEVER mode - database check). Above the threshold a different person holding `ledger:approve` must approve; requester can never approve (service + database, tested against the table owner path). Below-threshold direct posting only when configured, recorded as self-approved; reject (reason required), cancel (requester only) and expiry leave the ledger untouched. Policy changes need `ledger:policy` + reason and are audited before/after. Tests: tests/api/ledger-controls.test.ts (policy, threshold boundary 1000.00 / 1000.01, concurrency), tests/db/ledger-controls.test.ts (13), tests/platform/ledger-requests.test.ts (5)
V1-CTL-10 | DEC-012 | Approval requests are not ledger entries: pending requests cannot affect balances; posted journals stay immutable; correction by reversal only | M2 | IMPLEMENTED | Engineering | V1-CTL-09 | Trial balance and general ledger ignore pending requests; an approved request produces exactly one journal (idempotent); tests prove no UPDATE/DELETE path; the AI actor cannot request or approve. | - | Pending requests live in `journal_request` and are never read by trial balance / general ledger (asserted). An approved request produces exactly one journal (unique `journal.request_id`; idempotency key `request:<id>`; concurrent approvals and approve/reject/cancel races end with one outcome). Posted journals stay immutable and are corrected by reversal (tested); AI actors cannot request, approve or post (service + PostingService). Request content is immutable and decided requests final (trigger); no delete/truncate for runtime role or owner. Tests: tests/api/ledger-controls.test.ts, tests/db/ledger-controls.test.ts, tests/platform/ledger-requests.test.ts, tests/db/privileges.test.ts, tests/unit/architecture.test.ts (single writer of journal_request/ledger_policy)
V1-CTL-11 | DEC-012 | Opening-balance fence replaced by permission + approval (first-day rule retained) | M2 | IMPLEMENTED | Engineering | V1-CTL-07 | The first-day-of-first-period rule remains; a test shows the permission, approval and date rule all apply together. | - | The first-day-of-first-period rule is kept (validated at request creation and again at posting) together with the dedicated permission and the approval policy; a request dated elsewhere is refused with `opening_balance_date_invalid`. Tests: tests/api/ledger-controls.test.ts (validation), tests/platform/posting-service.test.ts
V1-FX-01 | DEC-009 | Functional currency: company base currency is the functional currency; cannot change once postings exist | M3 | IMPLEMENTED | Engineering | M1 | A company has exactly one functional currency; changing it after the first posting is refused by the database; documented. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Functional currency = `company.base_currency`; a database trigger refuses a change once the company has any journal (before the first journal it can change). Tests: tests/db/fx.test.ts (base currency), tests/platform/fx.test.ts
V1-FX-02 | DEC-009 | Transaction currency on documents and journal lines (ISO 4217 from the currency table) | M3 | IMPLEMENTED | Engineering | V1-FX-01 | A line carries its transaction currency; only known, active currencies accepted; functional-currency lines need no rate. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Transaction currency must exist in the `currency` table (`unknown_currency` otherwise); original amounts respect that currency's own minor units (service and database, e.g. yen has none). Tests: tests/platform/fx.test.ts (validation), tests/db/fx.test.ts (minor units)
V1-FX-03 | DEC-009 | Exchange-rate source and date: rates stored with source, rate date, provenance and verification status; lookup rule documented | M3 | IMPLEMENTED | Engineering (build); product owner (source decision) | DEC-016 | `exchange_rate` table (kind DAILY¦PERIOD, rate to 8 dp, publisher, series, URL, retrieved_at, source_kind MANUAL¦IMPORT, verification status, supersedes); manual entry needs source text and date and is audited; rows are immutable (corrections supersede); lookup = transaction date, else latest earlier DAILY rate within 7 days, else `exchange_rate_not_found`, never a future rate; CSV importer + `ExchangeRateSource` port with a fake; UNVERIFIED rates flagged and blockable by `ledger_policy.fx_block_unverified_rates`; live HTTP adapters NOT included (gate). | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | `exchange_rate`: kind DAILY¦PERIOD, 8-dp rate never rounded, MANUAL (source text mandatory, audited) or IMPORT (CSV file with publisher, series, URL, retrieved-at, batch), UNVERIFIED/VERIFIED (second person), immutable with supersession. Lookup: transaction date, else latest earlier DAILY rate within 7 days, else `exchange_rate_not_found`, never a later rate; ambiguity between series resolved by the company's default series; `fx_block_unverified_rates` policy. Live HTTP adapters are NOT included (gate). Tests: tests/platform/fx.test.ts (window boundaries day 0/+7/+8/-1, weekend, PERIOD, ambiguity, supersession, verification, import), tests/db/fx.test.ts, tests/api/fx.test.ts, tests/unit/fx-math.test.ts | Decision DEC-016 applied.
V1-FX-04 | DEC-009 | Original-currency values preserved on every foreign-currency line (amount, currency, rate, rate id) and immutable | M3 | IMPLEMENTED | Engineering | V1-FX-02, V1-FX-03 | Journal lines store original amount, currency and the rate used; a reversal reproduces them; the ledger refuses lines with an original amount but no rate and vice versa. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | `journal_line` stores original currency, original debit/credit, rate and rate id (all-or-none); immutable (ledger triggers); a reversal copies them with sides swapped; the line guard rejects a rate that is not the stored rate for the pair, a rate dated after the journal, a wrong side. Tests: tests/db/fx.test.ts, tests/platform/fx.test.ts (reversal), tests/api/fx.test.ts
V1-FX-05 | DEC-009 | Functional-currency postings: journals balance in the functional currency and per currency; rounding differences to a designated rounding account | M3 | IMPLEMENTED | Engineering | V1-FX-04 | For every journal sum(debit)=sum(credit) in functional currency; unbalanced converted lines get one visible FX-rounding line on the system account `FX_ROUNDING`, permitted difference one minor unit per line, else `rounding_tolerance_exceeded`; tests for within/beyond tolerance. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Foreign journals are converted per line and balanced in the functional currency; a visible system line on the designated FX-rounding account absorbs a difference of up to one minor unit per line (`rounding_tolerance_exceeded` beyond; `fx_rounding_account_missing` if unset); the foreign-currency amounts must balance too. Tests: tests/platform/fx.test.ts (rounding line 24.72 example), tests/unit/fx-math.test.ts (tolerance property), tests/db/fx.test.ts
V1-FX-06 | DEC-009 | Rounding rules: rate precision, per-line vs per-document conversion, rounding mode, minor units per currency | M3 | IMPLEMENTED | Engineering (build); product owner (policy) | DEC-017 | Rate stored to 8 dp unrounded; functional amount rounded per line, half-up, to the functional currency's minor units by one function with property tests (reverse conversion within tolerance; totals independent of line order; half-up boundary); VAT rounding left to M4. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | One `convert` function: rate x original rounded half-up to the functional minor units; rates stored to 8 dp; VAT rounding left to M4. Property-style tests: boundary (0.125 -> 0.13), minor units 0/2/3, reverse conversion within tolerance, totals independent of line order; database re-proves with `round()`. Tests: tests/unit/fx-math.test.ts, tests/db/fx.test.ts | Decision DEC-017 applied.
V1-FX-07 | DEC-009 | Realised FX gains and losses on settlement (receipts/payments against invoices/bills) | M3 | PARTIALLY IMPLEMENTED | Engineering | V1-FX-05, M5, M6 | `FxService.settle` posts the difference between the functional value carried and the value at the settlement rate to `FX_REALISED` exactly once; partial settlements prorate; tested with several rates (receipts/payments in M5/M6 call it). | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Realised FX engine `settle` delivered and unit-tested (full settlement clears the carried value exactly; partial settlements prorate with no residue; gains and losses; refusals). No posting path or endpoint until receipts and payments exist (M5/M6), so not yet exercised end to end. Tests: tests/unit/fx-math.test.ts M5a: Exercised end to end for credit-note allocations (M5a): carried amounts released by `releaseShare` (full remainder or prorated), difference posted as SALES_ALLOCATION_FX to the realised-FX account with receivables lines marked adjusts_currency; hand-calculated gain 20.00 and full-settlement 16.67 cases. Receipts and payments (M5b/M6) still to come. M5b: receipts settle foreign invoices with realised FX on every allocation, exercised end to end (two receipts at 0.90 and 0.80 against an invoice at 0.85: +30.00 / -20.00, net 10.00 = cash 860.00 less carried 850.00; no residue). Supplier payments are M6. | Engine in M3; used by receipts and payments in M5/M6 Decision DEC-018 applied.
V1-FX-08 | DEC-009 | Period-end revaluation of monetary items (unrealised) with auto-reversal | M3 | IMPLEMENTED | Engineering (build); product owner (policy) | V1-FX-05, DEC-018 | Explicit, previewed `revalue` action (`period:manage`) per period revalues foreign-currency monetary accounts at the period-end rate to `FX_UNREALISED`; auto-reversal dated the first day of the next period (immediately or by sweeper); idempotent per period via `fx_revaluation_run`; refused in locked periods; close needs acknowledgement if a balance is unrevalued; non-monetary items untouched. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Explicit, previewed revaluation per period (`period:manage`) of foreign-currency monetary accounts (by subtype) at the closing rate to the designated unrealised account; one journal (source FX_REVALUATION) and an auto-reversal on the next day (at once if that period is open, otherwise due and blocking close of the period containing its date); idempotent by carrying-amount comparison; concurrent runs post one journal; refused in closed/locked periods; non-monetary and P&L accounts untouched; close without revaluation needs `acknowledgeUnrevaluedFx`. Tests: tests/platform/fx.test.ts (revaluation, close controls, concurrency), tests/api/fx.test.ts | Decision DEC-018 applied.
V1-FX-09 | DEC-009 | Acceptance tests for reconciliation and reporting in multiple currencies | M3 | PARTIALLY IMPLEMENTED | Engineering | V1-FX-05..08 | Trial balance in functional currency balances; the sub-ledger in original currency revalued at the closing rate equals the control account; FX gain/loss report drills to journals. | Live rate adapters (gated); hedge accounting; forward contracts; net investments; intercompany eliminations | Reconciliation proven: after revaluation, original balance x closing rate equals the functional carrying amount per account (tests/platform/fx.test.ts); the functional-currency trial balance balances and the FX accounts' general ledger drills to the revaluation journal and its reversal (tests/api/fx.test.ts). A dedicated FX gain/loss report and multi-currency statements belong with reporting (M8). | Multi-currency reporting checks repeat in M8
V1-FX-10 | DEC-009 | Single-currency limitation is explicit until the foundation is implemented | M3 | IMPLEMENTED | Engineering | M1 | A journal request naming a currency other than the company base currency is refused with code `foreign_currency_not_supported` and a message pointing to the plan; OpenAPI and documentation state the limitation; tests cover it. | - | Superseded in part by M3: foreign-currency journals are now converted. The limitation that remains is explicit: opening balances and control adjustments are posted in the company currency only (`foreign_currency_not_supported`, message and OpenAPI updated). Tests: tests/api/ledger-controls.test.ts, tests/platform/fx.test.ts
V1-VAT-01 | DEC-010 | Effective-dated tax codes (code, treatment, direction, description) with source and verification status | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | `tax_code` (code, name, treatment, direction, reverse charge; immutable; unique per organisation); verification status lives on each rate version. Tests: tests/db/vat.test.ts, tests/platform/vat.test.ts, tests/api/vat.test.ts
V1-VAT-02 | DEC-010 | Effective-dated rates per tax code (no overlapping rates for one code), each with official source reference, retrieval date and UNVERIFIED/VERIFIED status; an UNVERIFIED rate cannot be activated | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | `tax_rate` versions: effective-dated, no overlap among current versions of a code (trigger), official source URL + provision + retrieval date mandatory, box mapping; changed only by supersession (UNVERIFIED again). Tests: tests/db/vat.test.ts, tests/platform/vat.test.ts
V1-VAT-03 | DEC-010 | Treatments: standard, reduced, zero-rated, exempt, outside the scope of VAT | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | STANDARD, REDUCED (rate > 0) and ZERO, EXEMPT, OUTSIDE_SCOPE (rate 0) enforced by the database; zero/exempt/outside lines carry their code with no VAT line; outside scope maps to no box. Tests: tests/platform/vat.test.ts, tests/db/vat.test.ts
V1-VAT-04 | DEC-010 | Sales VAT (output tax) on invoices; purchase VAT (input tax) on bills | M4 | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Output VAT (sales codes) and input VAT (purchase codes) on journal lines, with visible VAT lines on the configured accounts. Invoices and bills are documents (M5/M6), so 'on invoices/bills' is not yet possible. Tests: tests/platform/vat.test.ts, tests/api/vat.test.ts M5a: Sales invoices carry output VAT per line with the verified version at the document's tax point (M5a); purchase bills are M6.
V1-VAT-05 | DEC-010 | VAT on credit notes and debit notes with linkage to the original supply | M4 | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | A credit note entered as a debit on a sales code reduces output VAT (tested); linkage to the original supply needs documents (M5/M6). M5a: Sales credit notes adjust VAT at the rate version the invoice used, reported at the credit note's tax point (vat_rate_point proven by the database; workpaper test); purchase debit notes are M6. Rule UNVERIFIED (DEC-029).
V1-VAT-06 | DEC-010 | VAT-inclusive and VAT-exclusive entry; calculations exact, rounding rule documented and tested | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Exclusive (round(net x r/100)) and inclusive (round(gross x r/(100+r))) entry, per line half-up (DEC-025; rule UNVERIFIED vs HMRC); the database re-proves each VAT line at commit. Tests: tests/unit/vat-math.test.ts (boundaries, net+VAT = gross), tests/db/vat.test.ts, tests/platform/vat.test.ts
V1-VAT-07 | DEC-010 | Tax-point handling: supply date, invoice date, payment date; the rate and period are those of the tax point | M4 | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Explicit tax point per journal (defaults to the journal date) selects the rate version and the return period (stagger function tested). Determining it from supply/invoice/payment dates is a document matter (M5/M6). Tests: tests/platform/vat.test.ts, tests/unit/vat-math.test.ts M5a: Sales documents carry issue date, supply date and tax point (explicit or the issue date); the view flags taxPointReview when they differ; statutory derivation not automated (DEC-028).
V1-VAT-08 | DEC-010 | Control-account reconciliation: the VAT control account equals the sum of VAT lines by period; breaks are listed | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Workpaper reconciliation: movement on the VAT accounts by journal date versus VAT lines by tax point, difference listed with the entries that explain it (non-VAT postings, tax points outside the journal's period). Tests: tests/platform/vat.test.ts (hand-calculated -9.50 example), tests/api/vat.test.ts
V1-VAT-09 | DEC-010 | VAT-return workpaper (the nine-box figures with drill-down to transactions) - a workpaper, not a submission | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Nine-box workpaper by tax point with drill-down per box, the verified rules used (source and verifier) and an explicit 'not a return, not a submission' notice. Tests: tests/platform/vat.test.ts (all boxes against a hand-calculated synthetic scenario), tests/api/vat.test.ts
V1-VAT-10 | DEC-010 | Reverse-charge cases accommodated by the model (e.g. domestic reverse charge, imported services): a line can account for output and input VAT simultaneously | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Reverse-charge purchase codes post equal output and input VAT lines (RC_OUTPUT/RC_INPUT) proven equal by the database; the applicable cases are whatever verified rule versions the firm defines. Tests: tests/platform/vat.test.ts
V1-VAT-11 | DEC-010 | VAT treatment/rate is separate from VAT accounting scheme; scheme registry with STANDARD active and CASH / FLAT_RATE present but not implemented and not selectable | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Scheme registry (STANDARD implemented; CASH and FLAT_RATE registered, refused by the service and by a database check); codes and rates never encode the scheme. Tests: tests/platform/vat.test.ts, tests/db/vat.test.ts, tests/api/vat.test.ts, tests/unit/vat-math.test.ts
V1-VAT-12 | DEC-010 | Every tax rule records its official HMRC source, effective dates and who verified it; nothing is entered from memory | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Every rate version records source URL, provision and retrieval date, and who verified it, when, with notes (optionally an evidence document); verification is by a holder of `tax:rule-verify` other than the author (service and database); nothing is seeded. **The rules themselves are verified by the firm, not by this platform.** Tests: tests/db/vat.test.ts, tests/platform/vat.test.ts, tests/api/vat.test.ts
V1-VAT-13 | DEC-010 | VAT registration details on the company (number, effective date, return frequency, scheme) with validation | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Company VAT settings: registration, VRN (format), registration date, scheme, period length and stagger (month-end), output and input VAT accounts; audited with reason; VAT codes refused before registration. Tests: tests/platform/vat.test.ts, tests/api/vat.test.ts, tests/unit/vat-math.test.ts
V1-VAT-14 | DEC-010 | Posting validator enforces consistency of treatment, rate and amounts (V1-POST-05) | M4 | IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | PostingService VAT step plus the commit-time database proof (verified, current version of the line's code, covering the tax point; exact VAT amount; reverse-charge pair equal). Tests: tests/db/vat.test.ts, tests/platform/vat.test.ts
V1-VAT-15 | DEC-010 | Foreign-currency VAT: VAT amounts in the functional currency per the verified rule, with the original-currency amounts kept | M4 | MISSING | Engineering (build); qualified tax reviewer (rules) | M3; verified HMRC sources | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation. | Cash accounting; Flat Rate Scheme; partial exemption; capital goods scheme; margin schemes; OSS/import schemes; MTD submission (V5) | Not implemented by design: VAT on foreign-currency journals is refused (`vat_foreign_currency_not_supported`, service and database) until the rule on the currency of VAT amounts is verified.
V1-CON-01 | DEC-011 | Customer and supplier roles on the shared `contact`, with role-specific profile tables for differing fields | M4 | IMPLEMENTED | Engineering | V0 contacts (master data), V0 field encryption | Meets the requirement with API, permission, tenant-isolation and audit tests. | Contact merge; import from other systems (V11) | `contact_role` (CUSTOMER/SUPPLIER per company) with `customer_profile` (terms, credit limit, default currency) and `supplier_profile` (terms, default currency, default expense account, bank details); the database ties each profile to a role of the right kind and company. Tests: tests/api/contact-roles.test.ts, tests/db/contact-roles.test.ts
V1-CON-02 | DEC-011 | One contact may hold both roles; roles are added and removed with audit; removing a role is refused while open documents exist | M4 | PARTIALLY IMPLEMENTED | Engineering | V0 contacts (master data), V0 field encryption | Meets the requirement with API, permission, tenant-isolation and audit tests. | Contact merge; import from other systems (V11) | One contact holds both roles (tested); roles are created, changed, ended (with reason, never deleted) and reactivated with audit before/after. The rule 'ending is refused while open documents exist' cannot apply until documents exist (M5/M6) and is not yet implemented. Tests: tests/api/contact-roles.test.ts, tests/db/contact-roles.test.ts M5a: Ending a customer role is now refused while it has drafts or approved sales documents with an amount outstanding (tests/api/sales.test.ts); supplier documents follow in M6. M5b: unallocated receipts also count as open (ending refused).
V1-CON-03 | DEC-011 | Tenant and company scope enforced on roles and profiles (a company-level contact is invisible to other companies) | M4 | IMPLEMENTED | Engineering | V0 contacts (master data), V0 field encryption | Meets the requirement with API, permission, tenant-isolation and audit tests. | Contact merge; import from other systems (V11) | Roles and profiles are company-scoped (path permission per company, forced RLS per organisation); a company-linked contact cannot take a role in another company (service and database trigger); another company's path returns 404; another organisation sees zero rows. Tests: tests/api/contact-roles.test.ts, tests/db/contact-roles.test.ts
V1-CON-04 | DEC-011 | Documents keep a snapshot of the contact details used (name, address, VAT number) so history survives later edits | M4 | IMPLEMENTED | Engineering | V0 contacts (master data), V0 field encryption | Meets the requirement with API, permission, tenant-isolation and audit tests. | Contact merge; import from other systems (V11) | The snapshot (name, kind, VAT number, account code, primary address, capture time) is stored on each sales document at approval and is proven unchanged after a later edit of the contact. Tests: tests/platform/sales.test.ts, tests/db/sales.test.ts, tests/api/sales.test.ts, tests/unit/sales-math.test.ts
V1-CON-05 | DEC-011 | Sensitive profile data (bank details) encrypted at field level and never returned in lists, logs or audit snapshots | M4 | IMPLEMENTED | Engineering | V0 contacts (master data), V0 field encryption | Meets the requirement with API, permission, tenant-isolation and audit tests. | Contact merge; import from other systems (V11) | Supplier bank details are AES-256-GCM field-encrypted (AAD = role id); the database refuses plain digits; lists, the role view and audit records carry only a mask; full details only via GET bank-details with `contact:bank-details`, each read audited; a change resets to UNVERIFIED and must be verified by a different person (service and database check). Tests: tests/api/contact-roles.test.ts, tests/db/contact-roles.test.ts, tests/unit/architecture.test.ts (single writer, ciphertext touched only by the role service)
V1-PRIV-01 | DEC-013 | Session/challenge IP and user agent: collection, use, access and purpose traced; policy-controlled retention and deletion proposed; tests | Privacy track (parallel to V1) | PARTIALLY IMPLEMENTED | Engineering (investigation); DPO / legal (review and decisions) | V0 audit switch; retention schedule (DEC-003) | docs/legal/device-metadata-investigation.md traces every write and read with code references; characterisation tests fail if collection or exposure changes silently; a proposal for policy-controlled retention/deletion is written but NOT enabled; the item is not marked resolved until the privacy review is recorded. | Any deletion job (S4(b) is frozen) | Investigation delivered: docs/legal/device-metadata-investigation.md (7 collection points traced, 6 findings F-1..F-6, options A-F proposed and NOT enabled, review checklist); 10 characterisation tests in tests/api/device-metadata.test.ts; legal schedule corrected (raw IPs in Redis rate-limit keys). The finding is UNRESOLVED: no policy, deletion or lawful basis is approved; deletion stays frozen (S4(b)). | Never mark resolved without the recorded privacy review

## Milestones
Milestone | Scope | Status | Owner | Depends on | Acceptance | Deferred scope | Rows | Implemented
M1 | Ledger core: chart of accounts, period states, PostingService, journals, general ledger, trial balance | ACCEPTED (code baseline fae5270; DEC-008) | Engineering | - | v1-m1-acceptance.md | Foreign currency (M3), VAT (M4), source documents (M5+), UI (M9) | 33 | 26
M2 | Ledger controls: opening-balance permission, control-account adjustments, configurable second-person approval (DEC-012) | ACCEPTED (code baseline d98e3ed; DEC-015) | Engineering (build); product owner (approval thresholds, who may approve) | M1 accepted; V0 notification channel port (S2, delivered) for approver notifications; V0 documents + evidence links for supporting evidence | Section 3 of v1-plan.md; the M2 acceptance package (DEC-007) | Per-account approval rules and delegation; AI-assisted review (V6/V8); workflow-engine integration for multi-step approval | 5 | 5
M3 | Foreign-currency foundation: functional/transaction currency, rates, original-currency values, rounding, realised FX, revaluation (DEC-009) | ACCEPTED under delegation (code baseline c8fd8c0; DEC-019) | Engineering (build); product owner (rate source, policies) | M1 accepted; M2 accepted (DEC-015); Decisions recorded: rate source and window (DEC-016), rounding (DEC-017), revaluation and realised FX (DEC-018) | Section 5 of v1-plan.md (5.3) | Live HTTP rate adapters (network, publisher terms of use and format verification), hedge accounting, forward contracts, net investments and translation of foreign operations, intercompany eliminations, multi-currency bank statements beyond the account currency (M7), VAT-specific rate rules (M4) | 11 | 8
M4 | M4a contact roles (customer/supplier, DEC-011, DEC-023) and M4b VAT foundation - standard VAT accounting (DEC-010, DEC-021) | M4a VERIFIED (206b14d; v1-m4a-acceptance.md); M4b VERIFIED (6fb1938; v1-m4b-acceptance.md). VAT rules usable only after verification by the firm's holder of tax:rule-verify | Engineering (build); product owner + qualified tax reviewer (rule verification) | M1-M3 accepted (DEC-008, DEC-015, DEC-019); M4b: verification of each VAT rule by a holder of tax:rule-verify (DEC-021); primary sources not readable in this sandbox (DEC-022) | v1-plan.md section 6 (6.1 contact roles, 6.2 VAT); M4a package v1-m4a-acceptance.md | Cash accounting scheme, Flat Rate Scheme, partial exemption, capital goods scheme, margin schemes, OSS/import schemes, MTD submission (V5) | 25 | 16
M5 | Sales: invoices, credit notes, receipts; duplicate-document check | M5a VERIFIED (e698562); M5b implemented (receipts, allocation, realised FX, statement, ageing; acceptance package once verified); M5c (VAT on foreign-currency documents) to be specified (DEC-031) | Engineering | M2; M3; M4 | To be written when the milestone is specified | Recurring invoices, quotes, online payments, customer statements beyond the ledger view | 8 | 5
M6 | Purchases: bills, debit notes, payments, cash | PLANNED | Engineering | M5 patterns; M3; M4 | To be written when the milestone is specified | Payment runs, expense claims, purchase orders | 6 | 0
M7 | Bank accounts, statement import (async), transfers, charges, interest, reconciliation | PLANNED | Engineering | M5; M6 | To be written when the milestone is specified | Open Banking and bank feeds (V11), AI match suggestions (V6) | 15 | 0
M8 | Profit and loss, balance sheet, drill-down to documents, controls and alerts, FX reporting | PLANNED | Engineering | M3; M5; M6; M7 | To be written when the milestone is specified | FRS 102/105 statements (V2), comparatives and notes (V2) | 8 | 0
M9 | V1 UI slices behind feature flags (DEC-002) | PLANNED - runs in parallel from M2 | Engineering (front end) | API of the milestone each screen uses | Per screen: works against the real API, authorisation and tenant boundaries; accessibility checks | Mobile client portal (V7) | 1 | 0
Privacy track (parallel to V1) | Privacy finding on session / challenge IP and user agent (DEC-013) | INVESTIGATION DELIVERED - finding UNRESOLVED, awaiting privacy review (never resolved without it) | Engineering (investigation); DPO / legal (decisions) | DEC-003 retention review | V1-PRIV-01 | Any purge or deletion enabling (S4(b) frozen) | 1 | 0

## Summary
Status | Rows
IMPLEMENTED | 60
PARTIALLY IMPLEMENTED | 21
MISSING | 32
NOT APPLICABLE | 0
Total | 113
Plan version | 2
Commit | pending
CI | pending
Generated | 2026-10-13

## Plan history
Entry
v1 (2026-10-09): 77 rows, milestones M1-M6 (initial plan, commit 0aeff94 lineage).
v2 (2026-10-09, DEC-008..014): M1 accepted (fae5270). Milestones re-sequenced: new M2 (ledger controls), M3 (foreign currency), M4 (contact roles + VAT foundation); old M2 -> M5 (sales) + M4 (VAT/customers), old M3 -> M6, old M4 -> M7, old M5 -> M8, old M6 -> M9. Rows added: V1-FX-*, V1-VAT-*, V1-CON-*, V1-CTL-07..11, V1-PRIV-01. Each row now carries owner, dependencies, acceptance criteria and deferred scope.
v2.1 (2026-10-09): M2 ledger controls implemented. V1-CTL-07..11 -> Implemented with evidence; V1-CTL-06 evidence extended. No rows added or removed; M3+ unchanged and still gated. Not accepted until the product owner says so.
v2.2 (2026-10-12, DEC-015..018): M2 ACCEPTED (code baseline d98e3ed). M3 decisions recorded (rate source and window, rounding, revaluation/realised FX); M3 specification completed in v1-plan.md section 5 and ready to start. No rows added or removed. M4 remains gated by verification of tax rules from official sources.
v2.3 (2026-10-12): M3 foreign-currency foundation implemented. V1-FX-01..06, 08, 10 -> Implemented; V1-FX-07 and V1-FX-09 stay Partially implemented (settlement path needs M5/M6; FX report is M8). No rows added or removed. Not accepted until the product owner says so.
v2.4 (2026-10-12, DEC-019..024 under delegated authority): M3 accepted; M4 split into M4a (contact roles, implemented) and M4b (VAT). V1-CON-01, -03, -05 -> Implemented; V1-CON-02 and -04 Partially implemented (need documents, M5/M6). No rows added or removed.
v2.5 (2026-10-12, DEC-025): M4b VAT foundation implemented. V1-VAT-01, -02, -03, -06, -08..14 and V1-POST-05 -> Implemented; V1-VAT-04, -05, -07 Partially implemented (documents M5/M6); V1-VAT-15 stays Missing by design. No rule figures seeded.
v2.6 (2026-10-12, DEC-026..031): M5a sales documents implemented. V1-MOD-06, V1-EX-01, V1-CON-04 -> Implemented; V1-MOD-04, V1-EX-05, V1-CTL-02, V1-CTL-05 -> Partially implemented (receipts M5b; purchases M6; alert thresholds M8); evidence extended on V1-CON-02, V1-ARC-01, MAN-ACC-06, MAN-ACC-08, XP-07, V1-VAT-04/05/07, V1-FX-07, V1-CTL-06, V1-RPT-02. No rows added or removed.
v2.7 (2026-10-13, DEC-032): M5b receipts implemented. V1-MOD-08, V1-EX-03 -> Implemented; V1-MOD-04 -> Implemented (paid by receipts); evidence extended on V1-FX-07 (end to end on receipts; payments M6), V1-CON-02, XP-07. No rows added or removed.