## Summary
Item | Value
Report | docs/architecture/v1-readiness-report.md
Recommendation | V1 built and verified for its approved scope; NOT production-approved (DEC-006)
Last code commit verified | c0cad12
CI | https://github.com/mianshoaiblhr/uk-accounting-platform/actions/runs/38973214119 (success)
Clean clone | 1881 tests passed; e2e 21/21; OpenAPI drift 0
Matrix | 113 rows: Implemented 106, Partially 5, Missing 2
Legal references | Pointers, not legal advice; see the Legal sources sheet for which were confirmed

## Open rows
ID | Requirement | Status | Owner | Acceptance criteria
V1-MOD-12 | VAT foundation | MISSING | Engineering + qualified tax reviewer | Section 5 of v1-plan.md: all V1-VAT acceptance criteria met with verified sources.
MAN-ACC-09 | Tax and reporting rules are effective-dated/versioned | PARTIALLY IMPLEMENTED | Engineering + qualified tax reviewer | VAT rates and report mappings are effective-dated in the database with source and verification status; a test proves a rate change does not alter posted history.
V1-VAT-04 | Sales VAT (output tax) on invoices; purchase VAT (input tax) on bills | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation.
V1-VAT-05 | VAT on credit notes and debit notes with linkage to the original supply | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation.
V1-VAT-07 | Tax-point handling: supply date, invoice date, payment date; the rate and period are those of the tax point | PARTIALLY IMPLEMENTED | Engineering (build); qualified tax reviewer (rules) | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation.
V1-VAT-15 | Foreign-currency VAT: VAT amounts in the functional currency per the verified rule, with the original-currency amounts kept | MISSING | Engineering (build); qualified tax reviewer (rules) | Meets the requirement with tests: positive, negative, reversal, period-lock and effective-date boundary cases; sources verified and recorded before activation.
V1-PRIV-01 | Session/challenge IP and user agent: collection, use, access and purpose traced; policy-controlled retention and deletion proposed; tests | PARTIALLY IMPLEMENTED | Engineering (investigation); DPO / legal (review and decisions) | docs/legal/device-metadata-investigation.md traces every write and read with code references; characterisation tests fail if collection or exposure changes silently; a proposal for policy-controlled retention/deletion is written but NOT enabled; the item is not marked resolved until the privacy review is recorded.

## Tax reviewer
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Enter and verify a rate version for each tax code the firm will use (source URL, provision, retrieval date; verifier not the author) | DEC-021; docs/legal/m4b-vat-sources.xlsx; Settings > VAT codes (API: POST tax-codes/{id}/rates, POST tax-rates/{id}/verify) | V1-MOD-12, V1-VAT-04 | VAT Notice 700; VAT Act 1994 s.2
2 | Confirm the net and VAT box of each rate version | Rate version boxes; GET vat/workpaper | V1-VAT-04 | VAT Notice 700/12
3 | Confirm per-line half-up rounding (net, or the VAT fraction of the gross) | DEC-025; tests/unit/vat-math.test.ts | V1-VAT-04 | VAT Notice 700 (rounding)
4 | Confirm the tax-point rule (explicit or issue date; supply date flagged) or specify the derivation to automate | DEC-028; sales and purchase document screens (taxPointReview) | V1-VAT-07 | VAT Act 1994 s.6; HMRC VATTOS3600; Notice 700 ss.14-15
5 | Confirm credit and debit notes take the original document's rate version and are reported at their own tax point | DEC-029; tests/platform/sales.test.ts, purchases.test.ts | V1-VAT-05 | VAT Regs 1995 reg 38; HMRC VATREC13040, VATREC13120
6 | Decide which reverse-charge cases the firm sets up as purchase codes | VAT codes with reverseCharge = true; tests/platform/vat.test.ts | V1-VAT-10 | VAT Act 1994 s.8, s.55A; SI 2019/892; HMRC VATREVCON13000
7 | Give the rule for VAT on foreign-currency supplies (the M5c specification depends on it) | DEC-031; plan M5c | V1-VAT-15 | VAT Act 1994 Sch 6 para 11; HMRC VATVAL09500
8 | Review the nine-box workpaper of a test company against hand-calculated figures | GET vat/workpaper; tests/platform/vat.test.ts | V1-VAT-09 | VAT Notice 700/12

## Privacy (DEC-013)
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Read the device-metadata investigation (every write and read of IP address and user agent) | docs/legal/device-metadata-investigation.md; tests/api/device-metadata.test.ts | V1-PRIV-01 | UK GDPR art 5
2 | Decide the purpose and lawful basis for collecting session and challenge IP address and user agent | Investigation, proposal section | V1-PRIV-01 | UK GDPR art 6
3 | Decide the retention period and approve the deletion approach (frozen until approved, S4(b)) | docs/legal/retention-verification-schedule.xlsx | V1-PRIV-01 | UK GDPR art 5(1)(e); ICO storage limitation guidance
4 | Note IP addresses can be personal data for a website operator; rate-limit keys hold raw IP addresses | Investigation, Redis section | V1-PRIV-01 | CJEU C-582/14 Breyer (19 Oct 2016)

## Security reviewer
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Review the protection class of every table and the row-level security and privilege tests | docs/architecture/security-architecture.md; tests/db/privileges.test.ts
2 | Penetration test API and web tier on a non-production environment (sessions, MFA, Origin checks, idempotency, rate limits) | apps/api, apps/web; tests/api/*
3 | Review field encryption of bank details and key handling | contact-roles and bank services; tests/db/contact-roles.test.ts, tests/db/bank.test.ts
4 | Review the document pipeline (AV scan before use) and the CI security gates (CodeQL, audit, secret scan, Trivy) | CI runs on the release commit

## Infrastructure (AWS)
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Plan and apply infra/terraform in a non-production account; verify encryption, backups, private networking, IAM, logging | infra/terraform
2 | Set the S3 bucket CORS policy for presigned uploads (statement import) | infra/terraform storage; M9c acceptance, limitation 4
3 | Run the clean-clone and e2e suites against the deployed environment | scripts; tests/e2e
4 | Add a Terraform provider lock file (Dependabot's Terraform job fails without one); needs access to registry.terraform.io | infra/terraform/versions.tf

## Performance
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Load realistic volumes and measure posting, trial balance, statements, alerts and reconciliation suggestions | packages/accounting (reports, alerts, reconciliation)
2 | Choose indexes, caching or materialised balances from the measurements

## Product owner
# | Check | Where to look | Matrix row | Legal reference | Result (accept / amend / reject) | Reviewer | Date | Notes
1 | Accept V1 as built and verified for its scope, or list what is missing | docs/architecture/v1-readiness-report.md
2 | Name the qualified tax reviewer and the DPO / legal reviewer
3 | Decide MAN-ACC-09 (reporting mappings effective-dated in the database) with V2 planning | docs/architecture/v2-proposal.md | MAN-ACC-09
4 | Approve or amend the V2 proposal before V2 work starts | docs/architecture/v2-proposal.md

## Legal sources
Reference | Link | Check status
VAT Act 1994, s.6 (time of supply) | https://www.legislation.gov.uk/ukpga/1994/23/section/6 | confirmed by search 2026-10-17
VAT Act 1994, s.8 (reverse charge on services from abroad) | https://www.legislation.gov.uk/ukpga/1994/23/section/8 | standard address; open before relying on it
VAT Act 1994, s.55A (domestic reverse charge) | https://www.legislation.gov.uk/ukpga/1994/23/section/55A | standard address; open before relying on it
HMRC VATREVCON13000 (domestic reverse charge: law) | https://www.gov.uk/hmrc-internal-manuals/vat-reverse-charge-for-building-and-construction-services-manual/vatrevcon13000 | confirmed by search 2026-10-17
VAT Act 1994, Sch 6 para 11 (foreign currency) | https://www.legislation.gov.uk/ukpga/1994/23/schedule/6/paragraph/11 | standard address; open before relying on it
HMRC VATVAL09500 (foreign currency conversion) | https://www.gov.uk/hmrc-internal-manuals/vat-valuation/vatval09500 | confirmed by search 2026-10-17
VAT Regulations 1995 (SI 1995/2518), reg 38 | https://www.legislation.gov.uk/uksi/1995/2518/regulation/38 | standard address; open before relying on it
HMRC VATREC13040 (conditions of a valid credit note) | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13040 | confirmed by search 2026-10-17
HMRC VATREC13070 (reg 38: change in consideration) | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13070 | confirmed by search 2026-10-17
HMRC VATREC13120 (credit notes: case law) | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13120 | confirmed by search 2026-10-17
Case: British United Shoe Machinery Co Ltd (1977) VATTR 187 | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13120 | as summarised by HMRC
Case: Silvermere Golf and Equestrian Centre Ltd (1981) VATTR 106 | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13120 | as summarised by HMRC
Case: Highsize Ltd (LON/90/945) | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13120 | as summarised by HMRC
Case: Kwik Fit (GB) Ltd (1992) VATTR 427 | https://www.gov.uk/hmrc-internal-manuals/vat-trader-records/vatrec13120 | as summarised by HMRC
HMRC VATTOS3600 (actual tax points) | https://www.gov.uk/hmrc-internal-manuals/vat-time-of-supply/vattos3600 | confirmed by search 2026-10-17
VAT Notice 700/12 (filling in the VAT return) | https://www.gov.uk/guidance/how-to-fill-in-and-submit-your-vat-return-vat-notice-70012 | confirmed by search 2026-10-17
UK GDPR art 5 (principles) | https://www.legislation.gov.uk/eur/2016/679/article/5 | standard address; open before relying on it
UK GDPR art 6 (lawful basis) | https://www.legislation.gov.uk/eur/2016/679/article/6 | standard address; open before relying on it
ICO guidance: storage limitation | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/data-protection-principles/a-guide-to-the-data-protection-principles/storage-limitation/ | confirmed by search 2026-10-17
Case: CJEU C-582/14 Breyer v Bundesrepublik Deutschland (19 Oct 2016) | https://curia.europa.eu/juris/liste.jsf?num=C-582/14 | judgment confirmed by search; standard address