## V2 matrix
ID | Reference | Requirement | Milestone | Status | Owner | Dependencies | Acceptance criteria | Deferred scope | Evidence | Notes
V2-ARC-01 | V2 FRS Architecture | Reporting rules never hard-coded in transaction logic | V2-M1 | IMPLEMENTED | Engineering | ADR-62 | Statements, notes and validations come only from framework tables; an architecture test fails if transaction modules read them or if the report service reads source documents (ADR-63). | - | packages/accounting/src/statutory.ts, statutory-report.ts; tests/unit/architecture.test.ts ('no transaction module reads the reporting framework', 'statutory statements read the ledger and the reporting framework only', 'one writer per side'); tests/api/statutory.test.ts | Statements and validations come only from the framework tables; disclosure rules are stored as data and rendered in V2-M5 from the same tables. The expression interpreter has no code evaluation (architecture-tested).
V2-ARC-02 | V2 FRS Architecture | Standard -> effective date -> reporting map -> disclosure rules -> validation rules | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | DEC-053 | Each layer is a table keyed to an effective-dated standard version; a company's financial year selects one version; changing the version changes the output without code. | - | migration 20260119000000_v2_reporting_framework; tests/api/statutory.test.ts ('a second standard with another layout ... when the year switches to it') | Standard, effective-dated version, statement lines, map, disclosure rules and validation rules are tables keyed to the version; company_reporting_framework selects one per financial year; switching the year's version changed the output with no code change.
V2-ARC-03 | V2 FRS Architecture | Support FRS 102, FRS 105 and future standards without redesign | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-ARC-02 | Two synthetic standards with different layouts produce their own statements from the same ledger in tests; a third is added as data only. | - | tests/golden/v2-m1-micro-synthetic.json (version and alternative); tests/api/statutory.test.ts | Two synthetic standards with different layouts produce their own hand-calculated statements from one ledger. A third standard is a further set of API calls (no code path names a standard). No real FRS 102 or FRS 105 content is entered (DEC-052).
V2-ARC-04 | DEC-052 | Every standard rule sourced and verified by a second person; unverified rules give previews only | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | DEC-052 | Author cannot verify (service and database); verified records immutable; a change supersedes; previews carry verified=false and a notice; filing-ready output refuses unverified rules (V2-M6). | - | tests/api/statutory.test.ts ('verification by a second person'); tests/db/reporting-framework.test.ts ('verification: once, by a person other than the author ...'); tests/db/accounts-approval.test.ts ('the filing-ready package (V2-ARC-04) is refused under a version not verified by a second person ...'); tests/unit/accounts-approval.test.ts ('the package gate'); tests/api/accounts-approval.test.ts | Built and tested. The author cannot verify (service 403 and database CHECK). A verified version and its content are immutable (service 409 and database trigger), and changes supersede. Unverified previews carry verified=false and a PREVIEW ONLY notice. Since V2-M6c (DEC-070), the filing-ready package is refused unless the standard version and every size threshold set used were verified by a second person (service), and the database refuses a package under a version never verified. This row is the mechanism only: no real standard content or threshold is verified yet. That is Shoaib's verification in the platform (DEC-052, DEC-056); "ok done" and document reviews verify nothing (DEC-065).
MAN-ACC-09 | Manifest accounting controls (carried from V1) | Tax and reporting rules are effective-dated/versioned | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-ARC-02 | Reporting maps effective-dated in the database with source and verification status (decided in DEC-051); a test proves a later version does not alter an earlier year's output. | - | migration 20260119000000_v2_reporting_framework; tests/api/statutory.test.ts ('a change supersedes ... the earlier year keeps the version it was prepared under, and its figures') | Mechanism only: reporting maps are in the database per effective-dated, sourced version with verification status; after a later version replaced it, the 2025 preview still came from the version 2025 chose, with the same figures. V1 management statements keep the code registry (ADR-48). The rules the firm enters remain its own and unverified until its accountant verifies them (DEC-052).
V2-MOD-01 | V2 Modules | Year-end wizard | V2-M6 | IMPLEMENTED | Engineering | V2-M1 | The 14-step workflow (V2-YE rows) guides a financial year from lock to filing-ready package, each step showing its status from the underlying control. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts; tests/golden/v2-m6c-approval.json (docs/architecture/v2-m6c-golden-workings.xlsx re-derives every control, state and refusal of six phases with an independent implementation of the rules: 112 checks, 0 differences); tests/api/accounts-approval.test.ts; tests/unit/accounts-approval.test.ts; tests/db/accounts-approval.test.ts | Built in V2-M6b (DEC-069) and completed in V2-M6c (DEC-070): the 14-step workflow of a framework year. Each step's control is read from an existing control, with its dependencies, its state (DONE, LAPSED, BLOCKED, TODO, ATTENTION), its sign-offs or records, and the current step. Steps 1 to 11 are signed off by a preparer; steps 12 to 14 are done through the partner review, the client approval and the filing-ready package. Proven end to end on synthetic data.
V2-MOD-02 | V2 Modules | Trial balance mapping | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Every account of the trial balance lands on exactly one statutory line through the map or an override; unmapped and doubly mapped accounts are listed. | - | tests/api/statutory.test.ts (golden: unplacedAccounts empty; broken map lists the bank loan); tests/db/reporting-framework.test.ts (unique map entry and active override) | An override wins, else the most specific map entry, else the generic one (DEC-055). Double mapping cannot occur: the database allows one live entry per (version, V1 line, subtype) and one active override per account; the preview lists unmapped and misplaced accounts and proves the P&L against the ledger and the balance sheet to zero.
V2-MOD-03 | V2 Modules | Fixed assets | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | See V2-FA rows. | - | packages/accounting/src/fixed-assets.ts; tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | The register: classes, additions, depreciation, disposals, changes of estimate and the ledger reconciliation (V2-FA-01..08).
V2-MOD-04 | V2 Modules | Depreciation | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Depreciation runs post through the PostingService per class and method, once per period, reversible only by its own mirror; registry entry with five test categories. | - | packages/accounting/src/depreciation-math.ts, fixed-assets.ts (DepreciationService); tests/api/fixed-assets.test.ts ('the golden scenario'); tests/platform/fixed-assets.test.ts ('FIXED_ASSET_DEPRECIATION and its reversal'); tests/rules/posting-rules.ts | Runs post through the PostingService (FIXED_ASSET_DEPRECIATION): one journal, a pair of lines per class, one line per asset. A run must be later than every live run, one live run per date. Only the latest live run is reversed, by its own mirror. The source has its five test categories in the registry.
V2-MOD-05 | V2 Modules | Accruals | V2-M3 | IMPLEMENTED | Engineering | V2-M1 | Accruals post at period end and reverse on the first day of the next period (M3 pattern); listed with their evidence. | - | tests/golden/v2-m3a-adjustments.json (docs/architecture/v2-m3a-golden-workings.xlsx recomputes all 51 figures independently: 0 differences); tests/api/year-end.test.ts; tests/platform/year-end.test.ts; tests/db/year-end.test.ts | Accruals and accrued income post at the date with their reversal on the next day (ACCRUAL, ACCRUAL_AUTO_REVERSAL), which must fall in an open period. Evidence documents are linked to the item; a wrong accrual is cancelled by mirrors of both journals. Listed in the year-end register and reconciled to the ledger.
V2-MOD-06 | V2 Modules | Prepayments | V2-M3 | IMPLEMENTED | Engineering | V2-M1 | Prepayments released over their period by schedule; balance reconciles to the ledger. | - | tests/golden/v2-m3a-adjustments.json (docs/architecture/v2-m3a-golden-workings.xlsx recomputes all 51 figures independently: 0 differences); tests/api/year-end.test.ts; tests/platform/year-end.test.ts; tests/db/year-end.test.ts | Prepayments are set up from the expense account (posted) or linked to the payment that carries them, and released by release runs, straight line by day or by month. The balance reconciles to the ledger by account; unregistered postings are listed.
V2-MOD-07 | V2 Modules | Provisions | V2-M3 | IMPLEMENTED | Engineering | V2-M1 | Provisions recorded with basis and movement (made, used, released) and reconciled to the ledger. | - | tests/golden/v2-m3a-adjustments.json (docs/architecture/v2-m3a-golden-workings.xlsx recomputes all 51 figures independently: 0 differences); tests/api/year-end.test.ts; tests/platform/year-end.test.ts; tests/db/year-end.test.ts | A provision records its accounts and basis. Movements are made, used and released in date order and never take the balance below zero (service and database). The movement report gives opening, made, used, released and closing; the balance reconciles to the ledger. Discounting is not covered (DEC-059).
V2-MOD-08 | V2 Modules | Deferred income | V2-M3 | IMPLEMENTED | Engineering | V2-M1 | Deferred income released by schedule; balance reconciles to the ledger. | - | tests/golden/v2-m3a-adjustments.json (docs/architecture/v2-m3a-golden-workings.xlsx recomputes all 51 figures independently: 0 differences); tests/api/year-end.test.ts; tests/platform/year-end.test.ts; tests/db/year-end.test.ts | Deferred income is set up from the income account or linked, and released by release runs. The balance reconciles to the ledger.
V2-YEC-01 | v2-proposal section 4 (V2-M3) | Year-end closing journal to retained earnings | V2-M3 | IMPLEMENTED | Engineering | DEC-059 | The year's income and expense balances are closed to the retained-earnings account by one journal at the year end, reversible only by its mirror; every P&L figure (management P&L, statutory preview, FX report) excludes closing journals, and balance sheets include them, so statements reconcile before and after the close. | - | tests/golden/v2-m3b-close.json (docs/architecture/v2-m3b-golden-workings.xlsx recomputes all 152 figures independently: 0 differences); tests/api/year-end-close.test.ts; tests/platform/year-end-close.test.ts; tests/db/year-end-close.test.ts; tests/api/statutory.test.ts (preview unchanged by closes) | Added 2026-10-18 from the approved plan (DEC-059). Built in V2-M3b (DEC-060): one closing journal per financial year (aligned to accounting periods, at most 18 months, never overlapping a live close) moves every income and expense balance of the year to retained earnings; while it is live the PostingService and the database refuse income and expense dated in the year; it is corrected only by its mirror. The management P&L, the balance sheet lines, the statutory preview and the FX report leave closing journals out and read the same before and after a close; the trial balance and the balance sheet's trial-balance proof include them.
V2-MOD-09 | V2 Modules | Director/shareholder balances | V2-M4 | IMPLEMENTED | Engineering | V2-M1 | Director loan accounts per person with movements and the year-end balance; overdrawn balances and large movements flagged. | - | tests/golden/v2-m4-directors.json (docs/architecture/v2-m4-golden-workings.xlsx recomputes all 79 figures independently: 0 differences); tests/api/directors.test.ts; tests/platform/directors.test.ts; tests/db/directors.test.ts; tests/unit/directors.test.ts | Built in V2-M4 (DEC-062): a loan account per director or shareholder on a dedicated non-control ledger account (a director needs a DIRECTOR appointment); statements with every movement, its category and running balance, the lowest day-end balance and days overdrawn; review flags (overdrawn at the end and in the period; large movements and overdrawn beyond the firm's versioned thresholds, reported as not evaluated when unset). Reads the ledger only; no legal threshold is encoded.
V2-MOD-10 | V2 Modules | Related parties | V2-M4 | IMPLEMENTED | Engineering | V2-M1 | Related parties recorded with relationship and transactions for the year, available to the notes. | - | tests/golden/v2-m4-directors.json (docs/architecture/v2-m4-golden-workings.xlsx recomputes all 79 figures independently: 0 differences); tests/api/directors.test.ts; tests/platform/directors.test.ts; tests/db/directors.test.ts; tests/unit/directors.test.ts | Built in V2-M4 (DEC-062): a related-party register (counterparty, relationship, description, from and to dates; ended once) and a report per party for any range: sales and purchases net of VAT from its documents, cash paid and received from its cash transactions, owed by and owed to at the end from the control accounts, and its loan accounts, each with the journals behind it, as the input for the related-party note (V2-M5).
V2-MOD-11 | V2 Modules | Comparative periods | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Statements show the prior financial year on the same standard version, from the ledger. | - | tests/api/statutory.test.ts (golden comparative 2025 on the 2026 version) | The prior framework year (else the twelve months before) on the current year's version, from journal lines.
V2-MOD-12 | V2 Modules | Notes | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Notes rendered from verified disclosure rules with their figures from the ledger; required notes per size present. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts | Notes rendered by V2-M5a (DEC-063) from the version's wording (disclosure rules with section, order, template and omit-when-empty; verified and frozen with the version) and facts from the ledger (fixed-asset movements), the registers (provisions, advances to directors, related parties) and the preparer (employees, approval, company wording); a rule applies to the sizes it lists; missing facts are reported and keep the document incomplete. Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-MOD-13 | V2 Modules | Statutory statements | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | P&L and balance sheet in the layout of the chosen standard version; cash flow where the standard requires it. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts; tests/api/statutory.test.ts (V2-M1 golden); tests/golden/v2-m5b-size.json (docs/architecture/v2-m5b-golden-workings.xlsx recomputes every figure, limit, condition and status independently: 139 checks, 0 differences); tests/api/size-test.test.ts; tests/unit/size-test.test.ts; tests/db/size-test.test.ts; tests/golden/v2-m5c-cash-flow.json (docs/architecture/v2-m5c-golden-workings.xlsx recomputes every line, total and cash balance independently, with a direct-method check: 106 checks, 0 differences); tests/api/cash-flow.test.ts; tests/unit/cash-flow.test.ts; tests/db/cash-flow.test.ts | Statements in the layout of the chosen version (V2-M1 preview, now part of the accounts document with comparatives, V2-M5a). The size test that decides which statements and notes a year may use is built in V2-M5b (DEC-066): company-law thresholds as sourced data verified by a second person, the two-or-more-of-three conditions, the two-consecutive-years rule, short years, and whether the chosen entity size fits; proven on synthetic limits, and the draft UK thresholds are unverified. The cash flow statement is built in V2-M5c (DEC-067) and joins the statements for the sizes the version lists. Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-MOD-14 | V2 Modules | Review checklist | V2-M6 | IMPLEMENTED | Engineering | V2-M1 | Checklist built from the review flags (V2-RC rows) with sign-off per item. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Built in V2-M6a (DEC-068): the review checklist of a framework year lists the nine controls (V2-RC-01 to V2-RC-09), each CLEAR, OPEN, EXPLAINED, SIGNED_OFF or NOT_EVALUATED, with its flags, figures, drill-down and responses; sign-off per flag by a second person holding accounts:review; resolved flags keep their history; complete when every control is evaluated and every flag is signed off. Proven on synthetic data.
V2-MOD-15 | V2 Modules | Accounts approval | V2-M6 | IMPLEMENTED | Engineering | V2-M1 | Partner review then client approval recorded with person and time; approval locks the year's framework and figures. | - | tests/golden/v2-m6c-approval.json (docs/architecture/v2-m6c-golden-workings.xlsx re-derives every control, state and refusal of six phases with an independent implementation of the rules: 112 checks, 0 differences); tests/api/accounts-approval.test.ts; tests/unit/accounts-approval.test.ts; tests/db/accounts-approval.test.ts; tests/unit/architecture.test.ts ('approvals and packages have one writer ...') | Built in V2-M6c (DEC-070). The partner review is recorded by a second person holding accounts:review, who is not the one who signed off the accounts (service 403 and database trigger), against the fingerprint (SHA-256) of the accounts document; it lapses when the accounts change. The client's approval is recorded with the approving director, the date and an evidence document, and must equal the approval the accounts state (Companies Act 2006 s.414). It needs a live partner review and the year's periods closed, and in the same transaction it locks the periods (through the period service) and the year's framework. After it, facts, flag responses, workflow sign-offs and reviews for the year are refused and its periods cannot be unlocked (service and database). Proven on synthetic data. Not built: withdrawing an approval and amended accounts (a later decision).
V2-FA-01 | V2 Fixed Assets | Additions | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | Three kinds: POSTED (Dr cost / Cr a non-control offset), LINKED to the posting that already carries the cost (over-linking refused), TAKE_ON with accumulated depreciation. Reversal of a POSTED addition before any depreciation (VOID).
V2-FA-02 | V2 Fixed Assets | Disposals (with gain or loss) | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | Full disposals: catch-up to the disposal date, cost and accumulated depreciation removed, carrying amount and proceeds on the class disposal account; gain or loss = proceeds - carrying amount. Reversed by its mirror while no later run is live. Partial disposals are out of scope (DEC-058).
V2-FA-03 | V2 Fixed Assets | Depreciation methods (straight line, reducing balance) | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | packages/accounting/src/depreciation-math.ts; tests/unit/depreciation-math.test.ts; tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | Straight line and reducing balance, DAILY or MONTHLY convention; exact decimals; each charge = cumulative due (rounded half-up) - charged, so rounding never drifts.
V2-FA-04 | V2 Fixed Assets | Useful lives | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | Life in months per class default or per asset; for a take-on, the remaining life; changed prospectively by a change of estimate (append-only bases).
V2-FA-05 | V2 Fixed Assets | Residual value | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | tests/golden/v2-m2-fixed-assets.json (hand figures; docs/architecture/v2-m2-golden-workings.xlsx recomputes all 37 independently: 0 differences); tests/api/fixed-assets.test.ts; tests/platform/fixed-assets.test.ts; tests/db/fixed-assets.test.ts | Residual per asset (class default as a percentage of cost); straight line depreciates to it exactly; reducing balance never goes below it.
V2-FA-06 | V2 Fixed Assets | Asset classes | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | migration 20260120000000_v2_fixed_assets; tests/db/fixed-assets.test.ts ('classes'); tests/api/fixed-assets.test.ts ('classes name four accounts ...') | A class holds the four non-control accounts of the right type and subtype (database trigger) and the defaults for new assets; its code and accounts never move.
V2-FA-07 | V2 Fixed Assets | Tax vs accounting treatment kept apart | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | Capital allowances computations (V4) | tests/unit/architecture.test.ts ('depreciation never reads the tax fields'); tests/api/fixed-assets.test.ts ('tax fields are stored apart') | Tax category and tax cost stored on the asset for V4 (capital allowances); depreciation never reads them (architecture-tested); changing them changed no preview figure.
V2-FA-08 | V2 Fixed Assets | Reconciliation of the register to the ledger | V2-M2 | IMPLEMENTED | Engineering | V2-M1 | Implemented with service, database and API tests and a hand-calculated golden example; postings through the PostingService with the five test categories; register reconciles to the cost and depreciation accounts to the cent. | - | tests/api/fixed-assets.test.ts ('the register at 31.12.2026 ... reconciles', 'an unregistered posting ... reconciling item') | Per cost and accumulated-depreciation account at a date: register against ledger, with every posting the register neither made nor linked listed as a reconciling item; golden reconciles to the cent, a manual posting shows as a 250.00 difference.
V2-YE-01 | V2 Year-End Workflow | Lock/confirm period | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the bookkeeping cut-off: the year's periods cover it without gaps, no draft sales or purchase documents and no pending journal requests are dated in it (the periods are locked at approval, V2-M6c, because adjustments still post). Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-02 | V2 Year-End Workflow | Bank reconciliation | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is review control RC-08 (unreconciled bank) being clear or signed off. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-03 | V2 Year-End Workflow | Receivables review | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the customer flags of RC-05 (old receivables from the V1 aged report) being none or signed off, with RC-05 evaluated. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-04 | V2 Year-End Workflow | Payables review | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the supplier flags of RC-05 (old payables from the V1 aged report) being none or signed off, with RC-05 evaluated. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-05 | V2 Year-End Workflow | Fixed asset review | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the V2-M2 register reconciling to the ledger at the year end, with a live depreciation run as at the year end when an asset is in use. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-06 | V2 Year-End Workflow | Accrual/prepayment review | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the V2-M3a year-end register reconciling to the ledger at the year end. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-07 | V2 Year-End Workflow | Director balances | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is review control RC-06 (director loan movements) being clear or signed off. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-08 | V2 Year-End Workflow | VAT reconciliation | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the V1 VAT workpaper for the year having no unexplained reconciliation difference (not applicable when the company is not VAT registered). Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-09 | V2 Year-End Workflow | Suspense clearance | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is review control RC-07 (suspense) being clear or signed off. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-10 | V2 Year-End Workflow | Review adjustments | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the V2-M6a review checklist being complete (every control evaluated, every flag signed off). Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-11 | V2 Year-End Workflow | Generate accounts | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6b-workflow.json (docs/architecture/v2-m6b-golden-workings.xlsx re-derives every control and state of five phases with an independent implementation of the rules: 79 checks, 0 differences); tests/api/year-end-workflow.test.ts; tests/unit/year-end-workflow.test.ts; tests/db/year-end-workflow.test.ts | The step reads its status from an existing control: its control is the V2-M5 accounts document being complete and the V2-M5b size test verified and fitting the chosen size. Built in V2-M6b (DEC-069): the step shows its control (READY, ATTENTION with what needs doing, or NOT_APPLICABLE), records the preparer's sign-off with time, note and the control at the time, lapses when the control stops being ready, and is blocked until the steps it depends on are done (1 first; 2-9 after 1; 10 after 1-9; 11 after 10). Proven on synthetic data.
V2-YE-12 | V2 Year-End Workflow | Partner review | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6c-approval.json (docs/architecture/v2-m6c-golden-workings.xlsx re-derives every control, state and refusal of six phases with an independent implementation of the rules: 112 checks, 0 differences); tests/api/accounts-approval.test.ts; tests/unit/accounts-approval.test.ts; tests/db/accounts-approval.test.ts | Built in V2-M6c (DEC-070): done through the partner review, not signed off in the workflow (step_own_record). Its control is the accounts document being complete and, once reviewed, unchanged since the review (READY, or ATTENTION when the accounts changed: LAPSED). Recorded by a second person with accounts:review, with time and an optional note. It is blocked until steps 1 to 11 are all done (DEC-070 amends DEC-069, which had it after step 11 alone). Proven on synthetic data.
V2-YE-13 | V2 Year-End Workflow | Client approval | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | - | tests/golden/v2-m6c-approval.json (docs/architecture/v2-m6c-golden-workings.xlsx re-derives every control, state and refusal of six phases with an independent implementation of the rules: 112 checks, 0 differences); tests/api/accounts-approval.test.ts; tests/unit/accounts-approval.test.ts; tests/db/accounts-approval.test.ts | Built in V2-M6c (DEC-070): done through the client approval. Its control is a live partner review, the year's periods closed and the approval facts set; once approved, the accounts unchanged since the approval. It records the director, the date, the evidence, who recorded it and when. Blocked until the partner review is done; it locks the year. Proven on synthetic data.
V2-YE-14 | V2 Year-End Workflow | Filing-ready package | V2-M6 | IMPLEMENTED | Engineering | V2-M1..M5 | The step reads its status from the existing control (V1 reconciliation sign-off, ageing, VAT reconciliation, alerts, V2 registers), records the reviewer's sign-off with time and notes, and blocks the next step where the specification requires it. | iXBRL and Companies House filing (V3) | tests/golden/v2-m6c-approval.json (docs/architecture/v2-m6c-golden-workings.xlsx re-derives every control, state and refusal of six phases with an independent implementation of the rules: 112 checks, 0 differences); tests/api/accounts-approval.test.ts; tests/unit/accounts-approval.test.ts; tests/db/accounts-approval.test.ts | Built in V2-M6c (DEC-070): done through the filing-ready package, generated once per year by a preparer and stored write-once with its SHA-256. It holds the approved accounts document, the fingerprint, the framework and who verified it, the size test, the partner review and the client approval. It is refused unless the year is approved, the accounts are unchanged since then and every rule used was verified by a second person (V2-ARC-04). It is not a filing. Proven on synthetic data.
V2-OUT-01 | V2 Accounts Output | Profit and loss | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts; tests/api/statutory.test.ts (V2-M1 golden) | The P&L of the accounts document (V2-M5a) through the verified version, with the comparative, matched to the golden output to the cent (v2-m1 and v2-m5a goldens). Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-OUT-02 | V2 Accounts Output | Balance sheet | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts; tests/api/statutory.test.ts (V2-M1 golden) | The balance sheet of the accounts document (V2-M5a) through the verified version, with the comparative, matched to the golden output to the cent (v2-m1 and v2-m5a goldens). Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-OUT-03 | V2 Accounts Output | Cash flow where applicable | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5c-cash-flow.json (docs/architecture/v2-m5c-golden-workings.xlsx recomputes every line, total and cash balance independently, with a direct-method check: 106 checks, 0 differences); tests/api/cash-flow.test.ts; tests/unit/cash-flow.test.ts; tests/db/cash-flow.test.ts | Built in V2-M5c (DEC-067): the cash flow statement by the indirect method, from the ledger through the version's cash-flow classes, map and captions (version content, verified with it). Operating, investing and financing sections with gross receipts and payments where a class asks for them, the comparative year, the accounts of each line, and a proof against the movement in cash; it joins the accounts document for the sizes the version lists. An account the map does not place is shown as unclassified and keeps the document incomplete. Proven on a verified synthetic version with synthetic classes and captions; no real FRS 102 Section 7 classification or caption is entered or verified (DEC-052): that is for the named accountant.
V2-OUT-04 | V2 Accounts Output | Notes | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts | Notes in the accounts document (V2-M5a): text and tables rendered exactly as the golden output. Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-OUT-05 | V2 Accounts Output | Accounting policies | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts | Accounting policies are the POLICIES section of the accounts document (V2-M5a), rendered from the version's wording exactly as the golden output. Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-OUT-06 | V2 Accounts Output | Comparatives | V2-M1 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m1-micro-synthetic.json; tests/api/statutory.test.ts ('reproduces the hand-written P&L and balance sheet to the cent, with the comparative') | Matched to the cent through a verified synthetic version (synthetic layout, not a real standard).
V2-OUT-07 | V2 Accounts Output | Directors/reporting sections where applicable | V2-M5 | IMPLEMENTED | Engineering (build); qualified accountant (rules) | V2-M1 | Produced from the ledger through the verified framework and matched to the golden output to the cent. | - | tests/golden/v2-m5a-document.json (docs/architecture/v2-m5a-golden-workings.xlsx recomputes every figure, table and sentence independently: 62 checks, 0 differences); tests/api/accounts-document.test.ts; tests/unit/accounts-document.test.ts; tests/db/accounts-document.test.ts | Directors' report and balance-sheet statements are sections of the accounts document (V2-M5a), applied by entity size (a small-company section is left out for a micro-entity in the golden), with the directors and the approval facts. Proven on a verified synthetic version with synthetic wording; no real FRS 105, FRS 102 or Companies Act wording is entered or verified (DEC-052): that is for the named accountant.
V2-RC-01 | V2 Review Controls | Unexplained movements | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Manual and control-adjustment journals of the year at or above the firm's unexplained-movement setting, with the journal's figures and drill-down. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-02 | V2 Review Controls | Material changes | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Statutory lines fed by accounts, and the retained profit, that move from the comparative by at least the firm's amount and percentage settings, with current, comparative, change and percentage. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-03 | V2 Review Controls | Unusual balances | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | P&L accounts whose net for the year is on the wrong side (income in debit, expense in credit), closing journals left out. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-04 | V2 Review Controls | Negative balances | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Asset accounts (other than accumulated depreciation) in credit and liability accounts in debit at the year end. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-05 | V2 Review Controls | Old receivables/payables | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Customers and suppliers with amounts overdue beyond the firm's setting (30, 60 or 90 days) at the year end, from the V1 aged reports. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-06 | V2 Review Controls | Director loan movements | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Director and shareholder loan accounts carrying any V2-M4 flag for the year (overdrawn at the end or in the period, large movements, overdrawn beyond the firm's threshold), with closing, lowest and days overdrawn. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-07 | V2 Review Controls | Suspense | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Suspense accounts with a balance at the year end. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-08 | V2 Review Controls | Unreconciled bank | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Bank accounts in use at the year end without a signed reconciliation at the year end or with a difference, and bank ledger accounts with a balance but no bank account set up. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-RC-09 | V2 Review Controls | Missing supporting evidence | V2-M6 | IMPLEMENTED | Engineering | V1-M8 alerts, V2-M2..M4 | Raised on the year-end review with its figures and drill-down, thresholds as data, cleared or explained with a reason by a named reviewer. | - | tests/golden/v2-m6a-review.json (docs/architecture/v2-m6a-golden-workings.xlsx recomputes every flag and figure independently: 38 checks, 0 differences); tests/api/review.test.ts; tests/unit/review.test.ts; tests/db/review.test.ts | Manual and control-adjustment journals, approved purchase bills and cash payments of the year at or above the firm's evidence setting without a live evidence link to a document. Raised live by V2-M6a (DEC-068) on the review checklist of a framework year; settings are the firm's, versioned, and a control whose setting is not set is NOT_EVALUATED, never passed. Each flag is explained by a preparer (accounts:prepare) and signed off by a second person holding accounts:review; an explanation lapses when the figures change; the database repeats the second-person rule. Proven on synthetic data.
V2-TEST-01 | V2 Tests | Golden trial balances and expected statutory outputs | V2-M1 | PARTIALLY IMPLEMENTED | Engineering (build); qualified accountant (rules) | DEC-054 | Each scenario's expected statements and notes are hand-written data in tests/golden/ and matched to the cent; the named accountant reviews them before verifying the rules they exercise. | - | tests/golden/v2-m1-micro-synthetic.json; tests/api/statutory.test.ts; tests/golden/v2-m2-fixed-assets.json; tests/golden/v2-m3a-adjustments.json; tests/golden/v2-m3b-close.json; tests/golden/v2-m4-directors.json; tests/golden/v2-m5a-document.json; tests/golden/v2-m5b-size.json; tests/golden/v2-m5c-cash-flow.json; tests/golden/v2-m6a-review.json; tests/golden/v2-m6b-workflow.json (each recomputed independently in its docs/architecture/v2-m*-golden-workings.xlsx); tests/golden/v2-m6c-approval.json | One micro-entity scenario with two layouts, written by hand first and matched to the cent. One hand figure (the broken-map net assets) was wrong on first run and recalculated by hand (recorded in the golden file). Remaining: scenarios for FRS 102 Section 1A and years with fixed assets and accruals (V2-M2..M5); review of the expected outputs by the named accountant before any real rule is verified. Since then each milestone added a hand-written golden scenario with an independent workbook (V2-M2 to V2-M6c, including the size test over four years and a medium-sized company's cash flow statement over two years); DEC-057 and DEC-061 record Shoaib's review of the V2-M1 to V2-M3b goldens. Still remaining: an FRS 102 Section 1A scenario and the named accountant's review of the V2-M4 to V2-M6c goldens.
V2-DOD-01 | Manifest definition of done | V2 workflows usable in screens | V2-M7 | MISSING | Engineering | V2-M1..M6 | Every V2 module has screens behind accounts.production, real-browser tested (DEC-050 pattern). | - | tests/e2e/year-end.test.ts (V2-M7a: the year-end workspace, five real-browser tests); docs/architecture/v2-m7a-acceptance.md (each screen with its API routes) | Split into three slices (DEC-071). V2-M7a, the year-end workspace, is built: the workflow, the review checklist and settings, the accounts document with its facts and size test, and the approval and package. It is behind accounts.production and proven in a real browser (DEC-050): the main path from step 11 to the package, a refusal shown in the API's words, a reviewer with no action button, and the feature off. Still missing: V2-M7b, the registers (fixed assets, year-end adjustments, the closing journal, director loans and related parties), and V2-M7c, the reporting framework (standards, verification, thresholds, the framework of each year, the statutory preview and cash flow). Those modules work through the API only, so the row stays Missing until all three slices are accepted.

## Milestones
Milestone | Scope | Status | Owner | Depends on | Acceptance | Deferred scope | Rows | Implemented
V2-M0 | Decisions, plan, matrix, ADRs | RECORDED 2026-10-17 (DEC-051..054, ADR-62..64); qualified accountant named 2026-10-18: Shoaib (DEC-056) | Engineering | V2 approval (DEC-051) | v2-plan.md section 2 | - | 0 | 0
V2-M1 | Reporting framework as data | ACCEPTED under the delegation 2026-10-18 (v2-m1-acceptance.md; CI 39083312122 on fd0f556); rules unverified until Shoaib verifies them (DEC-056) | Engineering (build); qualified accountant (rules) | V2-M0 | v2-plan.md section 3.5; v2-m1-acceptance.md | Notes rendering, size test, cash flow (V2-M5); screens (V2-M7) | 9 | 8
V2-M2 | Fixed assets and depreciation | ACCEPTED under the delegation 2026-10-18 (v2-m2-acceptance.md; CI 39159238749 on da32ffc) | Engineering | V2-M1 | v2-plan.md section 4.4; v2-m2-acceptance.md | Capital allowances (V4) | 10 | 10
V2-M3 | Year-end adjustments and the closing journal | ACCEPTED under the delegation (DEC-059 split): V2-M3a 2026-10-18 (v2-m3a-acceptance.md; CI 39178258465 on f735149); V2-M3b 2026-10-19 (v2-m3b-acceptance.md; CI 39181318428 on 5ab27b8) | Engineering | V2-M2 | v2-plan.md sections 5.3 and 5b.4; v2-m3a-acceptance.md (V2-M3a); v2-m3b-acceptance.md (V2-M3b) | - | 5 | 5
V2-M4 | Director balances and related parties | ACCEPTED under the delegation 2026-10-19 (v2-m4-acceptance.md; CI 39251457210 on 87c8956) | Engineering | V2-M3 | v2-plan.md section 5c.3; v2-m4-acceptance.md | - | 2 | 2
V2-M5 | Statements and notes (FRS 105, FRS 102 1A, FRS 102) | ACCEPTED under the delegation (DEC-063, DEC-066 split): V2-M5a the accounts document 2026-10-19 (v2-m5a-acceptance.md; CI 39271179477 on 1492ff6); V2-M5b the size test 2026-10-20 (v2-m5b-acceptance.md; CI 39362598139 on 2277775); V2-M5c the cash flow statement 2026-10-20 (v2-m5c-acceptance.md; CI 39396072282 on 8fcee2c) | Engineering (build); qualified accountant (rules) | V2-M1; V2-M3; V2-M4 | v2-plan.md sections 5d.3, 5f.5 and 5g.4; v2-m5a-acceptance.md (V2-M5a); v2-m5b-acceptance.md (V2-M5b); v2-m5c-acceptance.md (V2-M5c) | iXBRL (V3) | 8 | 8
V2-M6 | Year-end workflow, review, approval, filing-ready package | SPLIT (DEC-068): V2-M6a review flags and the review checklist ACCEPTED 2026-10-21 (v2-m6a-acceptance.md; CI 39575388052 on 8646c7e); V2-M6b the 14-step year-end workflow ACCEPTED 2026-10-21 (v2-m6b-acceptance.md; CI 39595091384 on 9868fbc); V2-M6c partner review, client approval, locking and the filing-ready package ACCEPTED 2026-10-21 (v2-m6c-acceptance.md, DEC-070; CI 39608223030 on 120a949) | Engineering | V2-M5 | v2-plan.md sections 5h.3, 5i.4 and 5j.4; v2-m6a-acceptance.md (V2-M6a); v2-m6b-acceptance.md (V2-M6b); v2-m6c-acceptance.md (V2-M6c) | Filing (V3) | 26 | 26
V2-M7 | Screens behind accounts.production | SPLIT (DEC-071): V2-M7a the year-end workspace ACCEPTED 2026-10-21 (v2-m7a-acceptance.md; CI 39660002000 on 23b366f); V2-M7b the registers in progress (specified in v2-plan 5k.3, DEC-074); V2-M7c the reporting framework to be specified before its code | Engineering (front end) | each API milestone | v2-plan.md section 5k (V2-M7a); v2-m7a-acceptance.md; DEC-050 real-browser proof per slice; v2-plan.md section 5k.3 (V2-M7b) | - | 1 | 0

## Summary
Status | Rows
IMPLEMENTED | 59
PARTIALLY IMPLEMENTED | 1
MISSING | 1
NOT APPLICABLE | 0
Total | 61
Plan version | 4
Commit
CI
Generated | 2026-10-22

## Plan history
Entry
v1.0 (2026-10-17, DEC-051..054): matrix created from the V2 specification at V2-M0; 60 rows, all MISSING; MAN-ACC-09 carried from the V1 matrix (decided in DEC-051, built in V2-M1).
v1.1 (2026-10-18, V2-M1, DEC-055): reporting framework built. Missing -> Implemented: V2-ARC-01, V2-ARC-02, V2-ARC-03, MAN-ACC-09, V2-MOD-02, V2-MOD-11, V2-OUT-06. Missing -> Partially: V2-ARC-04 (filing-ready refusal in V2-M6), V2-TEST-01 (further scenarios; review by the named accountant). No real standard content entered or verified.
v1.2 (2026-10-18, DEC-056): V2-M1 evidence recorded (CI 39083312122 and CodeQL green on fd0f556; clean clone 1977 tests, e2e 21/21). Qualified accountant named: Shoaib; no row changes status from the naming alone.
v1.3 (2026-10-18, V2-M2, DEC-057/058): fixed assets built. Missing -> Implemented: V2-MOD-03, V2-MOD-04, V2-FA-01..08. Golden review of V2-M1 by Shoaib recorded (DEC-057); V2-TEST-01 stays Partially.
v1.3a (2026-10-18): V2-M2 evidence recorded (CI 39159238749 and CodeQL 39159238888 green on da32ffc; clean clone 2047 tests, e2e 21/21, OpenAPI drift 0).
v1.4 (2026-10-18, V2-M3a, DEC-059): year-end adjustments built. Missing -> Implemented: V2-MOD-05..08. Row added: V2-YEC-01, the year-end closing journal, which was in the approved V2-M3 scope but missing from the matrix (61 rows).
v1.4a (2026-10-18): V2-M3a evidence recorded (CI 39178258465 and CodeQL 39178258477 green on f735149; clean clone 2091 tests, e2e 21/21, OpenAPI drift 0).
v1.5 (2026-10-19, V2-M3b, DEC-060): year-end closing journal built. Missing -> Implemented: V2-YEC-01.
v1.5a (2026-10-19): V2-M3b evidence recorded (CI 39181318428 and CodeQL 39181318430 green on 5ab27b8; clean clone 2117 tests, e2e 21/21, OpenAPI drift 0). Milestone V2-M3 accepted.
v1.6 (2026-10-19, V2-M4, DEC-061/062): DEC-061 records the review of the V2-M2, V2-M3a and V2-M3b golden workings by Shoaib (no row changes status from it). Director and shareholder loan accounts and related parties built. Missing -> Implemented: V2-MOD-09, V2-MOD-10.
v1.6a (2026-10-19): V2-M4 evidence recorded (CI 39251457210 and CodeQL 39251456129 green on 87c8956; clean clone 2146 tests, e2e 21/21, OpenAPI drift 0). A V1-M9a screen defect found by the first clean clone (a stale answer overwriting a newer one) was fixed in 87c8956.
v1.7 (2026-10-19, V2-M5a, DEC-063): V2-M5 split; the accounts document built. Missing -> Implemented: V2-MOD-12, V2-OUT-01, V2-OUT-02, V2-OUT-04, V2-OUT-05, V2-OUT-07. Missing -> Partially: V2-MOD-13 (cash flow in V2-M5b). Mechanism proven on synthetic verified wording only; real standard wording remains the named accountant's (DEC-052).
v1.7a (2026-10-19): V2-M5a evidence recorded (CI 39271179477 and CodeQL 39271179462 green on 1492ff6; clean clone 2163 tests, e2e 21/21, OpenAPI drift 0).
v1.8 (2026-10-19, DEC-064): at the product owner's instruction engineering drafted FRS 105 (micro) and FRS 102 Section 1A (small) wording packs (content/standards/drafts), importable through the API as UNVERIFIED versions; review workbook v2-draft-wording-review.xlsx. No row changes status: the drafts are unverified and were not checked against the source text (DEC-052).
v1.8a (2026-10-19): draft wording packs evidence recorded (CI 39288936490 and CodeQL 39288936669 green on d08ecb3; clean clone 2175 tests, e2e 21/21, OpenAPI drift 0).
v1.9 (2026-10-20, V2-M5b, DEC-065/066): DEC-065 records the product owner's read of the draft wording packs (no verdicts; nothing verified). DEC-066 splits V2-M5 again (V2-M5c the cash flow statement) and builds the size test: threshold sets as sourced data verified by a second person, a version's turnover line, two facts for the earliest year, the size-test endpoint; draft UK thresholds importable as UNVERIFIED sets. No row changes status: V2-MOD-13 stays Partially implemented until the cash flow statement; V2-MOD-13 and V2-TEST-01 gain evidence.
v1.9a (2026-10-20): V2-M5b evidence recorded (CI 39362598139 and CodeQL 39362598131 green on 2277775; clean clone 2204 tests, e2e 21/21, OpenAPI drift 0).
v2.0 (2026-10-20, V2-M5c, DEC-067): the cash flow statement built (indirect method from the ledger; classes, map and captions as version content verified with it). Missing -> Implemented: V2-OUT-03. Partially -> Implemented: V2-MOD-13. V2-TEST-01 gains the V2-M5c golden. Proven on synthetic content only; no real FRS 102 classification or caption is entered or verified (DEC-052).
v2.0a (2026-10-20): V2-M5c evidence recorded (CI 39396072282 and CodeQL 39396072207 green on 8fcee2c; clean clone 2225 tests, e2e 21/21, OpenAPI drift 0).
v2.1 (2026-10-21, V2-M6a, DEC-068): V2-M6 split; review flags and the review checklist built. Missing -> Implemented: V2-RC-01 to V2-RC-09, V2-MOD-14. V2-TEST-01 gains the V2-M6a golden. Proven on synthetic data.
v2.1a (2026-10-21): V2-M6a evidence recorded (CI 39575388052 and CodeQL 39575387880 green on 8646c7e; clean clone 2256 tests, e2e 21/21, OpenAPI drift 0).
v2.2 (2026-10-21, V2-M6b, DEC-069): the 14-step year-end workflow built. Missing -> Implemented: V2-YE-01 to V2-YE-11. Missing -> Partially: V2-MOD-01 (steps 12-14 in V2-M6c). V2-TEST-01 gains the V2-M6b golden. Proven on synthetic data.
v2.2a (2026-10-21): V2-M6b evidence recorded (CI 39595091384 and CodeQL 39595091437 green on 9868fbc; clean clone 2275 tests, e2e 21/21, OpenAPI drift 0).
v2.3 (2026-10-21, V2-M6c, DEC-070): partner review, client approval, locking and the filing-ready package built. Missing -> Implemented: V2-MOD-15, V2-YE-12 to V2-YE-14. Partially -> Implemented: V2-MOD-01 (all 14 steps) and V2-ARC-04 (the filing-ready refusal of unverified rules; the mechanism only, no real rule verified). V2-TEST-01 gains the V2-M6c golden. The V2-M6b golden is revised for steps 12 to 14, with the revision recorded in the file. Proven on synthetic data.
v2.3a (2026-10-21): V2-M6c evidence recorded (CI 39608223030 and CodeQL 39608218001 green on 120a949; clean clone 2302 tests, e2e 21/21, OpenAPI drift 0; the first push 0731c7e failed typecheck and was fixed in 120a949).
v2.4 (2026-10-21, V2-M7a, DEC-071): the year-end workspace screens built (workflow, review, accounts, approval and package) and proven in a real browser. V2-DOD-01 stays Missing until V2-M7b and V2-M7c; its note records the slice. No status change.
v2.4a (2026-10-21): V2-M7a evidence recorded (CI 39660002000 and CodeQL 39660002001 green on 23b366f; clean clone 2302 tests, e2e 26/26, OpenAPI drift 0).
v2.4b (2026-10-21, DEC-072): engineering's data check (a review, not verification). Goldens 905 checks with 0 differences; 44 journals balanced; V2-M1 statements recomputed; 610 evidence paths present; thresholds confirmed against secondary sources; one wording finding (NOTE.CREDLONG). No status change.